## IMPLE. SCHE
IMPLEMENTATION SCHEDULE - WIND
ACTIVITIES | STATUS / EXPECTED COMMENCEMENT DATE | EXPECTED COMPLETION DATE
1. Acquisition of Land | COMPLETED | COMPLETED
2. Design & Engineering Activities | 20 MARCH 2025 | 17 APRIL 2025
3. Lease Right Transfer | 17 APRIL 2025 | 15 MAY 2025
4. Application for Power Evacuation (PE) Connectivity from GETCO | 15 MAY 2025 | 29 MAY 2025
5. Civil Constructions Activites for Wind Solar Hybrid Power Plant | 15 MAY 2025 | 19 JUNE 2025
6. Plant & Machineries
A. Finalization of P&M Suppliers | 17 APRIL 2025 | 15 MAY 2025
B. Orders to P&M Suppliers | 15 MAY 2025 | 19 JUNE 2025
C. Arrival of P&M | 19 JUNE 2025 | 24 JULY 2025
D. Errection of P&M | 24 JULY 2025 | 18 SEPTEMBER 2025
E. Utility Installation | 18 SEPTEMBER 2025 | 16 OCTOBER 2025
7. Approvals from Chief Electrical Inspectorate (CEIG) | 16 OCTOBER 2025 | 20 NOVEMBER 2025
8. Finishing & Trail Run | 20 NOVEMBER 2025 | 18 DECEMBER 2025
9. Commencement of Commercial Operation | 18 DECEMBER 2025 | 22 JANUARY 2026
IMPLEMENTATION SCHEDULE - SOLAR
ACTIVITIES | STATUS / EXPECTED COMMENCEMENT DATE | EXPECTED COMPLETION DATE
1. Acquisition of Land | COMPLETED | COMPLETED
2. Design & Engineering Activities | 20 MARCH 2025 | 17 APRIL 2025
3. Lease Right Transfer | 17 APRIL 2025 | 15 MAY 2025
4. Obtaining Approval from GEDA and Chief Electrical Inspectorate (CEIG) | 15 MAY 2025 | 29 MAY 2025
5. Civil Constructions Activites for Wind Solar Hybrid Power Plant | 15 MAY 2025 | 19 JUNE 2025
6. Plant & Machineries
A. Finalization of P&M Suppliers | 17 APRIL 2025 | 15 MAY 2025
B. Orders to P&M Suppliers | 15 MAY 2025 | 19 JUNE 2025
C. Arrival of P&M | 19 JUNE 2025 | 24 JULY 2025
D. Errection of P&M | 24 JULY 2025 | 18 SEPTEMBER 2025
E. Utility Installation | 18 SEPTEMBER 2025 | 16 OCTOBER 2025
7. Statutory Approvals from Chief Electrical Inspectorate (CEIG) | 16 OCTOBER 2025 | 20 NOVEMBER 2025
8. Finishing & Trail Run | 20 NOVEMBER 2025 | 18 DECEMBER 2025
9. Commencement of Commercial Operation | 18 DECEMBER 2025 | 22 JANUARY 2026