## Sheet1
MADHAV MARBLES AND GRANITES LIMITED | [9 empty] | 930.1769
ESTIMATED COST OF THE PROJECT
S.NO. PARTICULARS. | [5 empty] | COST ALREADY INCURRED |  |  | COST TO BE INCURRED |  |  | GRAND
[6 empty] | UPTO | [5 empty] | TOTAL
[7 empty] | Rupee |  |  | Rupee
[7 empty] | equivalent |  |  | equivalent
[7 empty] | of foreign |  |  | of foreign
[6 empty] | Rupee | exchange |  | Rupee | exchange
[6 empty] | Cost | cost | Total | Cost | cost | Total | (5+8)
-1 | -2 |  |  |  |  | -3 | -4 | -5 | -6 | -7 | -8 | -9
1 | LAND & SITE DEVELOPMENT :
| 1.1 | Cost excluding conveyance charges of |  |  |  | 0 | 0 |  | 165.1104 | 0 | 165.1104 | 165.11
|  | 48561.8729 | Sq.Mts. of land
to acquired Rs 340 per sq.metre
[6 empty] | 0 | 0 |  | 45.1625 | 0 | 45.1625 | 45.16
| 1.2 | Conversion Charges @Rs
|  | 93 |  | Z
| 1.3 | Registration and Stamp Duty |  |  |  | 0 | 0 |  | 4.9633 | 0 | 4.9633 | 4.96
|  | payable @ | 0.03 | %
| 1.4 | Cost of levelling & development L.S. |  |  |  | 0 | 0 | 0 | 15 | 0 | 15 | 15
| 1.5 | Cost of Laying Roads :
|  | 1.51 | Approach Roads |  |  | 0 | 0 | 0 | 5 | 0 | 5 | 5
|  | 1.52 | Internal Roads |  |  | 0 | 0 | 0 | 15 | 0 | 15 | 15
| 1.6 | Cost of Compound wall |  |  |  | 0 | 0 | 0 | 16.065 | 0 | 16.065 | 16.07
900 running metre @850
per running metere
| 1.7 | Cost of Gates (No. of gates 2) |  |  |  | 0 | 0 | 0 | 2 | 0 | 2 | 2
|  |  |  | TOTAL | -1 | 0 | 0 | 0 | 268.3012 | 0 | 268.3012 | 268.3
[5 empty] | Or Say | 0 | 0 | 0 | 268.3 | 0 | 268.3 | 268.3 | Lacs
[11 empty] | PAGE NO.= | 3
MADHAV MARBLES AND GRANITES LIMITED
2 | BUILDINGS :
| 2.1 | Main Factory Shed |  |  |  | 0 | 0 | 0 | 563.5 | 0 | 563.5 | 563.5
For Engineered Stone
| 2.2 | Administrative Block |  |  |  | 0 | 0 | 0 | 54 | 0 | 54 | 54
| 2.3 | D.G. Set & Electric Room |  |  |  | 0 | 0 | 0 | 12 | 0 | 12 | 12
| 2.4 | Security Room |  |  |  | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 2.5
| 2.5 | Underground Tank/ Overhead Tank |  |  |  | 0 | 0 | 0 | 2 | 0 | 2 | 2
| 2.6 | Sewerage & Drainage |  |  |  | 0 | 0 | 0 | 2 | 0 | 2 | 2
| 2.7 | Staff Quarters |  |  |  | 0 | 0 | 0 | 45 | 0 | 45 | 45
| 2.8 | Architect Fees |  |  |  | 0 | 0 | 0 | 13.62 | 0 | 13.62 | 13.62
[5 empty] | 3 | 0 | 0 | 0 | 694.62 | 0 | 694.62 | 694.62 | 0
[6 empty] | 0 | 0 | 0 | 695 | 0 | 695 | 695
2 | PLANT AND MACHINERY :
| 2.1 | Imported :
|  | 2.11 | FOB value |  |  | 0 | 0 | 0 | 1300.8575 | 0 | 1300.8575 | 1300.86
|  |  |  | Sub total | -1 | 0 | 0 | 0 | 1300.8575 | 0 | 1300.8575 | 1300.86 | Lacs
| 2.2 | Indigenous :
|  | 2.21 | F.O.R. Cost |  |  | 0 | 0 | 0 | 322.5 | 0 | 322.5 | 322.5
|  | 2.22 | Shipping freight and | [5 empty] | 16.26 | 0 | 16.26 | 16.26
insurance
|  | 2.23 | Clearing, loading, | [5 empty] | 9.66 | 0 | 9.66 | 9.66
unloading & transport
charges to factory site
| 2.3 | Foundation & installation charges |  |  |  | 0 | 0 | 0 | 110 | 0 | 110 | 110
on imported and indigenous machinery
|  |  |  | Sub total | -2 | 0 | 0 | 0 | 458.42 | 0 | 458.42 | 458.42 | Lacs
3 | MISCELLANEOUS FIXED ASSETS
| 3.1 | Indigenous :
|  | 3.11 | F.O.R. Cost |  |  | 0 | 0 | 0 | 320.25 | 0 | 320.25 | 320.25
|  |  |  | Sub total | -3 | 0 | 0 | 0 | 320.25 | 0 | 320.25 | 320.25 | Lacs

## Sheet2
Column1 | Column110 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35
ACTIVITIES |  | Column4: 2023-03-01; Column5: Apr23-Jun23; Column6: Jul23-Sep23; Column7: Oct23-Dec23; Column8: Jan24-Mar24; Column9: Apr24-Jun24; Column10: Jul24-Sep24; Column11: Oct24-Dec24; Column12: 2025-01-01; Column16: 2025-02-01; Column20: 2025-03-01; Column24: 2025-04-01; Column28: 2025-05-01; Column32: 2025-06-01
S.NO. |  |  | WEEKS | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | STATUTORY APPROVALS
1.1 | INCORPORATION | Column4: 2023-03-22
1.2 | BANK ACCOUNT OPENING | Column5: 2023-04-01
1.3 | LEI REGISTRATION | Column12: 2025-01-02
1.4 | IMPORTER EXPORTER CODE NO. | Column11: 2024-12-30
1.7 | APPLY FOR TEMPORARY | Column11: 2024-10-04
POWER CONNECTION
1.A | FINANCIAL ASSISTANCE
1.A.1 | PREPARATION OF PROJECT
REPORT
1.A.2 | APPLICATION FOR FINANCIAL
ASSISTANCE
1.A.3 | QUOTATION OF MACHINES
1.A.4 | APPRAISAL OF PROJECT
1.A.5 | IN PRINCIPLE APPROVAL
1.A.6 | FINAL SANCTION
ACTIVITIES |  | Column4: 2023-03-01; Column5: Apr23-Jun23; Column6: Jul23-Sep23; Column7: Oct23-Dec23; Column8: Jan24-Mar24; Column9: Apr24-Jun24; Column10: Jul24-Sep24; Column11: Oct24-Dec24; Column12: 2025-01-01; Column16: 2025-02-01; Column20: 2025-03-01; Column24: 2025-04-01; Column28: 2025-05-01; Column32: 2025-06-01
S.NO. |  |  | WEEKS | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
2 | LAND
2.1 | ACQUISITION OF LAND | Column4: 2023-03-31
2.2 | REGISTRATION OF LAND | Column4: 2023-03-31
2.4 | CONVERSION OF LAND | Column4: 2023-03-31
3 | BUILDING
3.2 | PREPARATION OF QUOTATION
3.3 | SHORTLISTING OF CONTRACTORS
3.4 | QUOTATION FROM CONTRACTORS
3.5 | AWARDING OF CONTRACT
3.6 | PLANT LAYOUT FROM SUPPLIER
3.7 | FOUNDATION DRAWING
3.8 | LAYOUT OF ELECTRICAL CABLES
3.9 | CONSTRUCTION OF BUILDING
ACTIVITIES |  | Column4: 2023-03-01; Column5: Apr23-Jun23; Column6: Jul23-Sep23; Column7: Oct23-Dec23; Column8: Jan24-Mar24; Column9: Apr24-Jun24; Column10: Jul24-Sep24; Column11: Oct24-Dec24; Column12: 2025-01-01; Column16: 2025-02-01; Column20: 2025-03-01; Column24: 2025-04-01; Column28: 2025-05-01; Column32: 2025-06-01
S.NO. |  |  | WEEKS | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
4 | PLANT & MACHINERY
4.1 | SELECTION OF PLANT & MACHINERY
4.2 | QUOTATIONS FROM VENDORS
4.3 | FINALISATION OF VENDORS
4.4 | PURCHASE & PAYMENT P&M
PLACEMENT OF ORDER
DELIVERY
5 | POWER CONNECTION
5.1 | APPLY FOR TEMPORARY | Column11: 2024-10-04
CONNECTION
5.2 | LAYING OF DEDICATED LINE
5.3 | PERMANENT CONNECTION
6 | COMMENCEMENT OF OPERATION