## Major Milestones - Dera Bassi
Project Schedule With Major Milestones
| Project Name: | Jwala Dera Bassi 5TPD CBG Project
| Project Start Date: | 2025-05-01
Current Date :
Weeks in Progress :
Sl no. | Major Milestones | Timeline |  | Duration (days) | Stakeholder Responsible | time axis 2025-05-01 to 2026-06-04
|  | Start Date | End Date | time axis 2025-05-01 to 2026-06-04
1 | Signing of EPC Contract | 2025-05-01 | 2025-05-01 | 1 | JB, EPC
2 | Signing of Sauter Contract | 2025-05-15 | 2025-05-15 | 1 | JB, Sauter
3 | Detailed Design by EPC | 2025-05-01 | 2025-06-15 | 45 | EPC
4 | Detailed Design by Sauter (Implementation Planning) | 2025-05-15 | 2025-06-29 | 45 | Sauter
5 | PO Placement of Digester tanks, Upgrading system and Pre-Treatment system | 2025-05-01 | 2025-05-10 | 9 | EPC
6 | Provisional Fire NOC | 2025-05-01 | 2025-05-30 | 29 | JB
7 | Building Plan Approvals | 2025-05-01 | 2025-06-30 | 60 | JB
8 | Ground Water Extraction Approval | 2025-05-01 | 2025-05-31 | 30 | JB
9 | Approval for Temporary Electricity Consumption | 2025-05-01 | 2025-05-31 | 30 | JB
10 | Mobilization of EPC team for civil | 2025-06-15 | 2025-06-30 | 15 | EPC
11 | On-site Civil work | 2025-07-01 | 2025-10-30 | 121 | EPC
12 | On-site Electrical Work | 2025-07-20 | 2025-08-30 | 41 | EPC
13 | On-site Piping Work | 2025-07-20 | 2025-09-30 | 72 | EPC
14 | Digester tank Foundation | 2025-07-01 | 2025-07-31 | 30 | EPC
15 | PO Placement of remaining items/ systems | 2025-08-01 | 2025-08-10 | 9 | EPC
16 | On-site receipt of Digester Tanks (lead time) | 2025-05-10 | 2025-08-08 | 90 | EPC
17 | On-site erection of Digester Tanks | 2025-08-09 | 2025-09-30 | 52 | EPC
18 | On-site receipt of Upgrading System (lead time) | 2025-05-10 | 2025-10-07 | 150 | EPC
19 | On-site receipt of Pre-Treatment system (lead time) | 2025-05-10 | 2025-09-07 | 120 | EPC
20 | On-site receipt of other equipment (lead time) | 2025-08-10 | 2025-10-09 | 60 | EPC
21 | Commence erection activity of other equipment | 2025-10-10 | 2026-01-30 | 112 | EPC
22 | Installation of Fire Fighting equipment/system | 2025-10-10 | 2025-11-29 | 50 | EPC
23 | Receipt of Sauter equipment on-site (lead time) | 2025-05-15 | 2025-12-01 | 200 | JB, Sauter
24 | Erection activity of Sauter equipment | 2025-12-02 | 2026-01-15 | 44 | Sauter, EPC
25 | Intergration & SCADA, Network connectivity | 2026-01-16 | 2026-01-31 | 15 | Sauter, EPC
26 | Consent to Operate | 2025-11-01 | 2026-01-30 | 90 | JB
27 | Other Mandatory Approvals (Fire NOC, Factory License, permanent Electricity ) | 2025-11-01 | 2026-01-30 | 90 | JB
28 | Dry Commissioning of equipment | 2026-02-15 | 2026-02-28 | 13 | JB, EPC, Sauter
29 | Innoculum, Feedstock availability & Troubleshooting | 2026-03-01 | 2026-03-31 | 30 | JB
30 | Full Commissioning & Performance Trials | 2026-04-01 | 2026-04-21 | 20 | JB, EPC, Sauter
31 | Commercial Operational Date (COD) | 2026-05-01 | 2026-05-01 | 1 | JB, EPC, Sauter