## Varanasi_EPC Package_SC
Payments Status Varanasi Project: EPC Package
S. No. | Service | AS per PO and BBU | [10 empty] | Total Payment incl GST |  | Remarks
|  | UOM | QTY | UNIT RATE | PO Amount | GST Amount as per PO | Total Amount incl GST as per PO | Billed QTY | Balance QTY | Bill Amount | GST Amount | Sucessful Completion of PG Test for Entire EPC Package |  | Balance Amount
10%
II | EPC Package_SC AS per PO No. 5500039567-109-2020 dated 22.12.2021 |  |  |  | 298900000 | 53802000 | 352702000 |  |  | 298900000 | 53802000 | 29890000 | 322812000 | 0 |  | 0
4 | Civil, Structure & Architectural Works | Lot | 1 | 298900000 | 298900000 | 53802000 | 352702000 |  | 1 | 298900000 | 53802000 | 29890000 | 322812000 | 0
A | Back Filling | [7 empty] | 0 |  |  |  |  | 0
A.1.1 | Backfilling with Compaction | Cum | 200000 | 400 | 80000000 | 14400000 | 94400000 | 200000 | 0 | 80000000 | 14400000 | 8000000 | 86400000 | 0
B | Boundary Wall | [7 empty] | 0 |  |  |  |  | 0
B.1 | PCC Work | [7 empty] | 0 |  |  |  |  | 0
B.1.1 | PCC for foundations | % | 100 | 39000 | 3900000 | 702000 | 4602000 | 100 | 0 | 3900000 | 702000 | 390000 | 4212000 | 0
B.2 | RCC (Including Reinforcement & Form Work) | [7 empty] | 0 |  |  |  |  | 0
B.2.1 | Raft for Boundary wall | Nos | 160 | 44687.5 | 7150000 | 1287000 | 8437000 | 160 | 0 | 7150000 | 1287000 | 715000 | 7722000 | 0
B.2.2 | Column above Raft to PB-1 bottom of Boundary wall | Nos | 160 | 36562.5 | 5850000 | 1053000 | 6903000 | 160 | 0 | 5850000 | 1053000 | 585000 | 6318000 | 0
B.2.3 | Plinth Beam of Boundary wall | R.Mtr | 1000 | 2925 | 2925000 | 526500 | 3451500 | 1000 | 0 | 2925000 | 526500 | 292500 | 3159000 | 0
B.2.4 | Column above Plinth Beam up to top of Coping | Nos | 160 | 18281.25 | 2925000 | 526500 | 3451500 | 160 | 0 | 2925000 | 526500 | 292500 | 3159000 | 0
B.2.5 | Coping RCC Over Wall | R.Mtr | 1000 | 975 | 975000 | 175500 | 1150500 | 1000 | 0 | 975000 | 175500 | 97500 | 1053000 | 0
B.3 | Masonary Work | [7 empty] | 0 |  |  |  |  | 0
B.3.1 | Brick Masonary | R.Mtr | 1000 | 3250 | 3250000 | 585000 | 3835000 | 1000 | 0 | 3250000 | 585000 | 325000 | 3510000 | 0
B.4 | Plaster | [7 empty] | 0 |  |  |  |  | 0
B.4.1 | Wall Plastering-Both Sides | % | 100 | 32500 | 3250000 | 585000 | 3835000 | 100 | 0 | 3250000 | 585000 | 325000 | 3510000 | 0
B.5 | Painting (Inner & Outer) | [7 empty] | 0 |  |  |  |  | 0
B.5.1 | Painting inside walls | % | 100 | 8125 | 812500 | 146250 | 958750 | 100 | 0 | 812500 | 146250 | 81250 | 877500 | 0
B.5.2 | Painting out side of walls | % | 100 | 8125 | 812500 | 146250 | 958750 | 100 | 0 | 812500 | 146250 | 81250 | 877500 | 0
B.6 | Fencing Work | [7 empty] | 0 |  |  |  |  | 0
B.6.1 | Fencing | % | 100 | 6500 | 650000 | 117000 | 767000 | 100 | 0 | 650000 | 117000 | 65000 | 702000 | 0
C | PILLING | [7 empty] | 0 |  |  |  |  | 0
C.1 | Civil Construction | [7 empty] | 0 |  |  |  |  | 0
C.1.1 | Installation of RCC 600 mm dia Cast-in-situ bored pile including reinforcement & concrete | % | 100 | 568925 | 56892500 | 10240650 | 67133150 | 100 | 0 | 56892500 | 10240650 | 5689250 | 61443900 | 0
C.1.2 | Vertical load test on single pile | Nos | 2 | 4375000 | 8750000 | 1575000 | 10325000 | 2 | 0 | 8750000 | 1575000 | 875000 | 9450000 | 0
C.1.3 | Tension load test on single pile | Nos | 2 | 4375000 | 8750000 | 1575000 | 10325000 | 2 | 0 | 8750000 | 1575000 | 875000 | 9450000 | 0
C.1.4 | Horizontal load test on single pile | Nos | 2 | 4375000 | 8750000 | 1575000 | 10325000 | 2 | 0 | 8750000 | 1575000 | 875000 | 9450000 | 0
C.1.5 | Routine test on single pile | Nos | 3 | 1452500 | 4357500 | 784350 | 5141850 | 3 | 0 | 4357500 | 784350 | 435750 | 4706100 | 0
D | CMS Building | [7 empty] | 0 |  |  |  |  | 0
D.1 | PCC Works | [7 empty] | 0 |  |  |  |  | 0
D.1.1 | PCC for Pile Caps | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.1.2 | PCC for Grade Slab | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2 | RCC Works | [7 empty] | 0 |  |  |  |  | 0
D.2.1 | RCC for Pile Caps | % | 100 | 10000 | 1000000 | 180000 | 1180000 | 100 | 0 | 1000000 | 180000 | 100000 | 1080000 | 0
D.2.2 | RCC Column from Raft top to Plinth beam bottom | % | 100 | 7500 | 750000 | 135000 | 885000 | 100 | 0 | 750000 | 135000 | 75000 | 810000 | 0
D.2.3 | RCC Plinth beam | % | 100 | 7500 | 750000 | 135000 | 885000 | 100 | 0 | 750000 | 135000 | 75000 | 810000 | 0
D.2.4 | Columns up to 1st roof slab 5.2 mt level(bottom) including lintel beam | % | 100 | 25000 | 2500000 | 450000 | 2950000 | 100 | 0 | 2500000 | 450000 | 250000 | 2700000 | 0
D.2.5 | RCC for 1st Floor Roof slab casting @ 5.35 mt level | % | 100 | 35000 | 3500000 | 630000 | 4130000 | 100 | 0 | 3500000 | 630000 | 350000 | 3780000 | 0
D.2.6 | RCC Columns from 9.85 mt lvl to 2nd roof slab bottom icluding tie beam | % | 100 | 25000 | 2500000 | 450000 | 2950000 | 100 | 0 | 2500000 | 450000 | 250000 | 2700000 | 0
D.2.7 | RCC for 2nd roof slab casting @ 10.60 mt | % | 100 | 25000 | 2500000 | 450000 | 2950000 | 100 | 0 | 2500000 | 450000 | 250000 | 2700000 | 0
D.2.8 | Brick Masonry work | % | 100 | 22500 | 2250000 | 405000 | 2655000 | 100 | 0 | 2250000 | 405000 | 225000 | 2430000 | 0
D.2.9 | Plaster out-side walls | % | 100 | 17500 | 1750000 | 315000 | 2065000 | 100 | 0 | 1750000 | 315000 | 175000 | 1890000 | 0
D.2.10 | Plaster in-side walls | % | 100 | 17500 | 1750000 | 315000 | 2065000 | 100 | 0 | 1750000 | 315000 | 175000 | 1890000 | 0
D.2.11 | Floor tiles ground floor | % | 100 | 12500 | 1250000 | 225000 | 1475000 | 100 | 0 | 1250000 | 225000 | 125000 | 1350000 | 0
D.2.12 | Floor Tiles 1st floor | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2.13 | Battery room tiles | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2.14 | Water proofing of roofs | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2.15 | Out side bldg Drains and plinth protection | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2.16 | Painting of building outside | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2.17 | Painting of Building inside | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
D.2.18 | Sanitary Work & Plumbing Work | % | 100 | 2500 | 250000 | 45000 | 295000 | 100 | 0 | 250000 | 45000 | 25000 | 270000 | 0
D.2.19 | Toilets floor tiles,and dado | % | 100 | 2500 | 250000 | 45000 | 295000 | 100 | 0 | 250000 | 45000 | 25000 | 270000 | 0
E | PLANT SHED AREA | [7 empty] | 0 |  |  |  |  | 0
E.1 | PCC Works | [7 empty] | 0 |  |  |  |  | 0
E.1.1 | PCC for Pile Caps | % | 100 | 32000 | 3200000 | 576000 | 3776000 | 100 | 0 | 3200000 | 576000 | 320000 | 3456000 | 0
E.1.2 | PCC for Grade Slab | % | 100 | 32000 | 3200000 | 576000 | 3776000 | 100 | 0 | 3200000 | 576000 | 320000 | 3456000 | 0
E.2 | RCC Works | [7 empty] | 0 |  |  |  |  | 0
E.2.1 | RCC for Pile Caps | % | 100 | 100000 | 10000000 | 1800000 | 11800000 | 100 | 0 | 10000000 | 1800000 | 1000000 | 10800000 | 0
E.2.2 | RCC Column from Pile cap to Bolt Bottom | % | 100 | 40000 | 4000000 | 720000 | 4720000 | 100 | 0 | 4000000 | 720000 | 400000 | 4320000 | 0
E.2.3 | RCC Column from Bolt Bottom to TOC incl.foundation bolts | % | 100 | 40000 | 4000000 | 720000 | 4720000 | 100 | 0 | 4000000 | 720000 | 400000 | 4320000 | 0
E.2.4 | RCC flooring inside shed area | % | 100 | 80000 | 8000000 | 1440000 | 9440000 | 100 | 0 | 8000000 | 1440000 | 800000 | 8640000 | 0
E.2.5 | IPS flooring | % | 100 | 56000 | 5600000 | 1008000 | 6608000 | 100 | 0 | 5600000 | 1008000 | 560000 | 6048000 | 0
E.2.6 | Grouting | % | 100 | 20000 | 2000000 | 360000 | 2360000 | 100 | 0 | 2000000 | 360000 | 200000 | 2160000 | 0
F | MSW PIT AREA CIVIL WORK | [7 empty] | 0 |  |  |  |  | 0
F.1 | PCC Works | [7 empty] | 0 |  |  |  |  | 0
F.1.1 | PCC for Foundation | % | 100 | 8800 | 880000 | 158400 | 1038400 | 100 | 0 | 880000 | 158400 | 88000 | 950400 | 0
F.2 | RCC Works | [7 empty] | 0 |  |  |  |  | 0
F.2.1 | RCC for Foundation | % | 100 | 26400 | 2640000 | 475200 | 3115200 | 100 | 0 | 2640000 | 475200 | 264000 | 2851200 | 0
F.2.2 | RCC Wall - 1st Lift | % | 100 | 17600 | 1760000 | 316800 | 2076800 | 100 | 0 | 1760000 | 316800 | 176000 | 1900800 | 0
F.2.3 | RCC Wall - 2nd Lift | % | 100 | 13200 | 1320000 | 237600 | 1557600 | 100 | 0 | 1320000 | 237600 | 132000 | 1425600 | 0
F.2.5 | IPS flooring | % | 100 | 13200 | 1320000 | 237600 | 1557600 | 100 | 0 | 1320000 | 237600 | 132000 | 1425600 | 0
F.2.6 | Grouting | % | 100 | 8800 | 880000 | 158400 | 1038400 | 100 | 0 | 880000 | 158400 | 88000 | 950400 | 0
G | PELLET SILO AREA CIVIL WORK | [7 empty] | 0 |  |  |  |  | 0
G.1 | PCC Works | [7 empty] | 0 |  |  |  |  | 0
G.1.1 | PCC for Foundation | % | 100 | 700 | 70000 | 12600 | 82600 | 100 | 0 | 70000 | 12600 | 7000 | 75600 | 0
G.2 | RCC Works | [7 empty] | 0 |  |  |  |  | 0
G.2.1 | RCC for Foundation(Raft) including Tie Beam | % | 100 | 2100 | 210000 | 37800 | 247800 | 100 | 0 | 210000 | 37800 | 21000 | 226800 | 0
G.2.2 | RCC Column above Raft to Plinth Beam Bottom | % | 100 | 1750 | 175000 | 31500 | 206500 | 100 | 0 | 175000 | 31500 | 17500 | 189000 | 0
G.2.3 | RCC Plinth Beam | % | 100 | 1400 | 140000 | 25200 | 165200 | 100 | 0 | 140000 | 25200 | 14000 | 151200 | 0
G.2.4 | RCC Column Above Plinth Beam to TOC incl.Bolts | % | 100 | 700 | 70000 | 12600 | 82600 | 100 | 0 | 70000 | 12600 | 7000 | 75600 | 0
G.2.5 | Grouting | % | 100 | 350 | 35000 | 6300 | 41300 | 100 | 0 | 35000 | 6300 | 3500 | 37800 | 0
H | INERT SILO AREA CIVIL WORK | [7 empty] | 0 |  |  |  |  | 0
H.1 | PCC Works | [7 empty] | 0 |  |  |  |  | 0
H.1.1 | PCC for Foundation | % | 100 | 700 | 70000 | 12600 | 82600 | 100 | 0 | 70000 | 12600 | 7000 | 75600 | 0
H.2 | RCC Works
H.2.1 | RCC for Foundation-Raft | % | 100 | 2100 | 210000 | 37800 | 247800 | 100 | 0 | 210000 | 37800 | 21000 | 226800 | 0
H.2.2 | RCC Column above Raft to Plinth Beam Bottom | % | 100 | 1750 | 175000 | 31500 | 206500 | 100 | 0 | 175000 | 31500 | 17500 | 189000 | 0
H.2.3 | RCC Plinth Beam | % | 100 | 1400 | 140000 | 25200 | 165200 | 100 | 0 | 140000 | 25200 | 14000 | 151200 | 0
H.2.4 | RCC Column Above Plinth Beam with Bolts | % | 100 | 700 | 70000 | 12600 | 82600 | 100 | 0 | 70000 | 12600 | 7000 | 75600 | 0
H.2.5 | Grouting | % | 100 | 350 | 35000 | 6300 | 41300 | 100 | 0 | 35000 | 6300 | 3500 | 37800 | 0
I | EQUIPMENT FOUNDATION CIVIL WORK
I.1 | PCC Works
I.1.1 | PCC for Foundation | % | 100 | 6500 | 650000 | 117000 | 767000 | 100 | 0 | 650000 | 117000 | 65000 | 702000 | 0
I.2 | RCC Works | [12 empty] | 0
I.2.1 | RCC for Foundation-Raft including Tie beam if any | % | 100 | 19500 | 1950000 | 351000 | 2301000 | 100 | 0 | 1950000 | 351000 | 195000 | 2106000 | 0
I.2.2 | RCC Column/Pedestal above Raft to Plinth Beam Bottom,if any | % | 100 | 16250 | 1625000 | 292500 | 1917500 | 100 | 0 | 1625000 | 292500 | 162500 | 1755000 | 0
I.2.3 | RCC Plinth Beam, if any | % | 100 | 13000 | 1300000 | 234000 | 1534000 | 100 | 0 | 1300000 | 234000 | 130000 | 1404000 | 0
I.2.4 | RCC Column Above Plinth Beam with Bolts | % | 100 | 6500 | 650000 | 117000 | 767000 | 100 | 0 | 650000 | 117000 | 65000 | 702000 | 0
I.2.5 | Grouting | % | 100 | 3250 | 325000 | 58500 | 383500 | 100 | 0 | 325000 | 58500 | 32500 | 351000 | 0
J | WEIGH BRIDGE AREA CIVIL WORK
J.1 | PCC Works
J.1.1 | PCC for Foundation | % | 100 | 1000 | 100000 | 18000 | 118000 | 100 | 0 | 100000 | 18000 | 10000 | 108000 | 0
J.1.2 | PCC for Grade Slab | % | 100 | 1000 | 100000 | 18000 | 118000 | 100 | 0 | 100000 | 18000 | 10000 | 108000 | 0
J.2 | RCC Works
J.2.1 | RCC for Foundation-Raft | % | 100 | 2000 | 200000 | 36000 | 236000 | 100 | 0 | 200000 | 36000 | 20000 | 216000 | 0
J.2.2 | RCC Column/Pedestal including bolts | % | 100 | 2500 | 250000 | 45000 | 295000 | 100 | 0 | 250000 | 45000 | 25000 | 270000 | 0
J.2.3 | RCC Grade Slab | % | 100 | 3000 | 300000 | 54000 | 354000 | 100 | 0 | 300000 | 54000 | 30000 | 324000 | 0
J.2.4 | Grouting | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
K | ROADS & DRAIN
K.1 | WMM Laying for Roads | [8 empty] | 0 | 0 | 0 | 0 | 0
K.1.1 | WMM-1st layer of thickness 200 mm | % | 100 | 15000 | 1500000 | 270000 | 1770000 | 100 | 0 | 1500000 | 270000 | 150000 | 1620000 | 0
K.1.2 | WMM-2nd layer of thickness 125 mm | % | 100 | 10000 | 1000000 | 180000 | 1180000 | 100 | 0 | 1000000 | 180000 | 100000 | 1080000 | 0
K.2 | PCC Works | [8 empty] | 0 | 0 | 0 | 0 | 0
K.2.1 | PCC for Roads | % | 100 | 10000 | 1000000 | 180000 | 1180000 | 100 | 0 | 1000000 | 180000 | 100000 | 1080000 | 0
K.2.2 | PCC for Drains | % | 100 | 1000 | 100000 | 18000 | 118000 | 100 | 0 | 100000 | 18000 | 10000 | 108000 | 0
K.3 | RCC Works for Roads | % | 100 | 40000 | 4000000 | 720000 | 4720000 | 100 | 0 | 4000000 | 720000 | 400000 | 4320000 | 0
K.4 | Brick Masonry for Drains | % | 100 | 4000 | 400000 | 72000 | 472000 | 100 | 0 | 400000 | 72000 | 40000 | 432000 | 0
L | WATER HARVESTING & GREEN AREA | [8 empty] | 0 | 0 | 0 | 0 | 0
L.1 | 300 mm dia Boring | % | 100 | 700 | 70000 | 12600 | 82600 | 100 | 0 | 70000 | 12600 | 7000 | 75600 | 0
L.2 | PCC Works for filter media & Harvesting Sump | % | 100 | 1000 | 100000 | 18000 | 118000 | 100 | 0 | 100000 | 18000 | 10000 | 108000 | 0
L.3 | RCC WORKS | [8 empty] | 0 | 0 | 0 | 0 | 0
L.3.1 | RCC Works for filter media & Harvesting Sump | % | 100 | 3300 | 330000 | 59400 | 389400 | 100 | 0 | 330000 | 59400 | 33000 | 356400 | 0
L.4 | HORTICULTURE | [8 empty] | 0 | 0 | 0 | 0 | 0
L.4.1 | Water Bodies | % | 100 | 2500 | 250000 | 45000 | 295000 | 100 | 0 | 250000 | 45000 | 25000 | 270000 | 0
L.4.2 | Haze | % | 100 | 7500 | 750000 | 135000 | 885000 | 100 | 0 | 750000 | 135000 | 75000 | 810000 | 0
L.4.3 | Trees | % | 100 | 5000 | 500000 | 90000 | 590000 | 100 | 0 | 500000 | 90000 | 50000 | 540000 | 0
M | TOPOGRAPHY SURVEY | SET | 1 | 500000 | 500000 | 90000 | 590000 | 1 | 0 | 500000 | 90000 | 50000 | 540000 | 0
N | GEO TECHNICAL INVESTIGATION | SET | 1 | 1000000 | 1000000 | 180000 | 1180000 | 1 | 0 | 1000000 | 180000 | 100000 | 1080000 | 0
O | LEACHATE & EFFLUENT TREATMENT PLANT CIVIL WORK
O.1 | LECHATE SUMP
O.1.1 | PCC Works for foundations | % | 100 | 150 | 15000 | 2700 | 17700 | 100 | 0 | 15000 | 2700 | 1500 | 16200 | 0
O.2 | RCC Works for foundations
O.2.1 | RCC for Raft | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.2 | RCC Wall - 1st Lift | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.3 | RCC Wall - 2nd Lift | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.4 | RCC for Raft-2nd Stage | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.5 | RCC Wall - 1st Lift | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.6 | RCC Wall - 2nd Lift | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.7 | RCC Wall - 3rd Lift | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2.8 | RCC Wall - 4th Lift | % | 100 | 200 | 20000 | 3600 | 23600 | 100 | 0 | 20000 | 3600 | 2000 | 21600 | 0
O.2 | EFLUENT TREATMENT PLANT
O.2.1 | PCC Works for LTP TANKS & PLATFORM foundations | % | 100 | 250 | 25000 | 4500 | 29500 | 100 | 0 | 25000 | 4500 | 2500 | 27000 | 0
O.2.2 | PCC Works for ETP foundations | % | 100 | 2500 | 250000 | 45000 | 295000 | 100 | 0 | 250000 | 45000 | 25000 | 270000 | 0
O.2.3 | RCC Works for LTP TANKS & PLATFORM foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
O.2.4 | RCC Works for ETP foundations | % | 100 | 2000 | 200000 | 36000 | 236000 | 100 | 0 | 200000 | 36000 | 20000 | 216000 | 0
P | MISCELLANEOUS WORKS-NOT COVERED IN ABOVE WORKS | LOT
P.1 | PCC Works | [8 empty] | 0 | 0 | 0 | 0 | 0
P.1.1 | PCC Works for MSW foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.2 | PCC Works for Inert Conveyor foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.3 | PCC Works for Security Gate foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.4 | PCC Works for Worker Toilet Room | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.5 | PCC Works for Rest Room | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.6 | PCC Works for Fire Tanks | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.7 | PCC Works for Fire Pump Foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.8 | PCC Works for Equipment Room Foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.9 | PCC Works for Fire Pipe Pedestal Foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.10 | PCC Works for Transformer Foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.1.11 | PCC Works for Septic & Soak Pit Foundations | % | 100 | 500 | 50000 | 9000 | 59000 | 100 | 0 | 50000 | 9000 | 5000 | 54000 | 0
P.2 | RCC Works
P.2.1 | PCC Works for MSW foundations | % | 100 | 1500 | 150000 | 27000 | 177000 | 100 | 0 | 150000 | 27000 | 15000 | 162000 | 0
P.2.2 | PCC Works for Inert Conveyor foundations | % | 100 | 1500 | 150000 | 27000 | 177000 | 100 | 0 | 150000 | 27000 | 15000 | 162000 | 0
P.2.3 | PCC Works for Security Gate foundations | % | 100 | 1500 | 150000 | 27000 | 177000 | 100 | 0 | 150000 | 27000 | 15000 | 162000 | 0
P.2.4 | PCC Works for Worker Toilet Room | % | 100 | 1500 | 150000 | 27000 | 177000 | 100 | 0 | 150000 | 27000 | 15000 | 162000 | 0
P.2.5 | PCC Works for Rest Room | % | 100 | 1500 | 150000 | 27000 | 177000 | 100 | 0 | 150000 | 27000 | 15000 | 162000 | 0
P.2.6 | PCC Works for Fire Tanks | % | 100 | 1500 | 150000 | 27000 | 177000 | 100 | 0 | 150000 | 27000 | 15000 | 162000 | 0
P.2.7 | PCC Works for Fire Pump Foundations | % | 100 | 1100 | 110000 | 19800 | 129800 | 100 | 0 | 110000 | 19800 | 11000 | 118800 | 0
P.2.8 | PCC Works for Equipment Room Foundations | % | 100 | 1100 | 110000 | 19800 | 129800 | 100 | 0 | 110000 | 19800 | 11000 | 118800 | 0
P.2.9 | PCC Works for Fire Pipe Pedestal Foundations | % | 100 | 1100 | 110000 | 19800 | 129800 | 100 | 0 | 110000 | 19800 | 11000 | 118800 | 0
P.2.10 | PCC Works for Transformer Foundations | % | 100 | 1100 | 110000 | 19800 | 129800 | 100 | 0 | 110000 | 19800 | 11000 | 118800 | 0
P.2.11 | PCC Works for Septic & Soak Pit Foundations | % | 100 | 1100 | 110000 | 19800 | 129800 | 100 | 0 | 110000 | 19800 | 11000 | 118800 | 0
Q | SIDE SLOPE PROTECTION
Q.1 | PCC Works
Q.1.1 | PCC for Verical bands | % | 100 | 3024 | 302400 | 54432 | 356832 | 100 | 0 | 302400 | 54432 | 30240 | 326592 | 0
Q.1.2 | PCC for Horizontal bands(op & Bottom) | % | 100 | 3024 | 302400 | 54432 | 356832 | 100 | 0 | 302400 | 54432 | 30240 | 326592 | 0
Q.2 | Stone Masonry Works | % | 100 | 13952 | 1395200 | 251136 | 1646336 | 100 | 0 | 1395200 | 251136 | 139520 | 1506816 | 0
5 | Training Charges

## Bhopal_EPC Package_SC
Payments Status Bhopal Project: EPC Package
S. No. | Service | AS per PO and BBU | [10 empty] | Total Payment incl GST |  | Remarks
|  | UOM | QTY | UNIT RATE | PO Amount | GST Amount as per PO | Total Amount incl GST as per PO | Billed QTY | Balance QTY | Bill Amount | GST Amount | Sucessful Completion of PG Test for Entire EPC Package |  | Balance Amount
10%
II | EPC Package_SC AS per PO No. 5500045006-109-2C02 dated 16.12.2024 |  |  |  | 430340660 | 77461318.8 | 507801978.8 |  |  | 95436412.4 | 17178554.232 | 9543641.24 | 103071325.392 | 334904247.6 |  | 395187012.168
1 | Local Transportation including port clearance and port charges and Inland insurance charges for Main Equipments | Set | 1 | 5000000 | 5000000 | 900000 | 5900000 | 0 | 1 | 0 | 0 | 0 | 0 | 5000000
2 | Installation Services for Main Equipment excluding factory Fabricated Structures
A | EQUIPMENT FOR MAIN PLANT
i | Main Equipment excluding Factory Fabricated Steel Structure | Lot | 1 | 51840260 | 51840260 | 9331246.8 | 61171506.8 | 0 | 1 | 0 | 0 | 0 | 0 | 51840260
ii | Erection of Factory Fabricated Steel Structures | Lot | 1 | 15000000 | 15000000 | 2700000 | 17700000 | 0 | 1 | 0 | 0 | 0 | 0 | 15000000
B | Civil, Structure & Architectural Works | Lot | 1
A | Roads with shoulder
1 | GSB & WMM (CH 00.00 to CH 221.00) | % | 100 | 22100 | 2210000 | 397800 | 2607800 | 86.43 | 13.57 | 1910103 | 343818.54 | 191010.3 | 2062911.24 | 299897
2 | DLC (CH 00.00 to CH 221.00) | % | 100 | 18950 | 1895000 | 341100 | 2236100 | 86.43 | 13.57 | 1637848.5 | 294812.73 | 163784.85 | 1768876.38 | 257151.5
3 | PQC (CH 00.00 to CH 221.00) | % | 100 | 47360 | 4736000 | 852480 | 5588480 | 86.43 | 13.57 | 4093324.8 | 736798.464 | 409332.48 | 4420790.784 | 642675.2
4 | Shoulder (CH 00.00 to CH 221.00) | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
5 | GSB & WMM (CH 221.00 to CH 442.00) | % | 100 | 22050 | 2205000 | 396900 | 2601900 | 100 | 0 | 2205000 | 396900 | 220500 | 2381400 | 0
6 | DLC (CH 221.00 to CH 442.00) | % | 100 | 18950 | 1895000 | 341100 | 2236100 | 100 | 0 | 1895000 | 341100 | 189500 | 2046600 | 0
7 | PQC (CH 221.00 to CH 442.00) | % | 100 | 47400 | 4740000 | 853200 | 5593200 | 100 | 0 | 4740000 | 853200 | 474000 | 5119200 | 0
8 | Shoulder (CH 221.00 to CH 442.00) | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
9 | GSB & WMM (CH 442.00 to CH 663.00) | % | 100 | 22050 | 2205000 | 396900 | 2601900 | 100 | 0 | 2205000 | 396900 | 220500 | 2381400 | 0
10 | DLC (CH 442.00 to CH 663.00) | % | 100 | 18950 | 1895000 | 341100 | 2236100 | 100 | 0 | 1895000 | 341100 | 189500 | 2046600 | 0
11 | PQC (CH 442.00 to CH 663.00) | % | 100 | 47400 | 4740000 | 853200 | 5593200 | 100 | 0 | 4740000 | 853200 | 474000 | 5119200 | 0
12 | Shoulder (CH 442.00 to CH 663.00) | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
13 | GSB & WMM (CH 663.00 to CH 886.00) | % | 100 | 22050 | 2205000 | 396900 | 2601900 | 100 | 0 | 2205000 | 396900 | 220500 | 2381400 | 0
14 | DLC (CH 663.00 to CH 886.00) | % | 100 | 18950 | 1895000 | 341100 | 2236100 | 47.98 | 52.02 | 909221 | 163659.78 | 90922.1 | 981958.68 | 985779
15 | PQC (CH 663.00 to CH 886.00) | % | 100 | 47400 | 4740000 | 853200 | 5593200 | 47.98 | 52.02 | 2274252 | 409365.36 | 227425.2 | 2456192.16 | 2465748
16 | Shoulder (CH 663.00 to CH 886.00) | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
17 | GSB & WMM, Connecting roads to shed (~ 205m) | % | 100 | 15780 | 1578000 | 284040 | 1862040 |  | 100 | 0 | 0 | 0 | 0 | 1578000
18 | DLC, Connecting roads to shed (~ 205m) | % | 100 | 12625 | 1262500 | 227250 | 1489750 |  | 100 | 0 | 0 | 0 | 0 | 1262500
19 | PQC, Connecting roads to shed (~ 205m) | % | 100 | 25260 | 2526000 | 454680 | 2980680 |  | 100 | 0 | 0 | 0 | 0 | 2526000
20 | Shoulder Connecting roads to shed (~ 205m) | % | 100 | 3160 | 316000 | 56880 | 372880 |  | 100 | 0 | 0 | 0 | 0 | 316000
21 | GSB & WMM, Peripheral road (~ 264m) | % | 100 | 22100 | 2210000 | 397800 | 2607800 | 100 | 0 | 2210000 | 397800 | 221000 | 2386800 | 0
22 | DLC, Peripheral road (~ 264m) | % | 100 | 18950 | 1895000 | 341100 | 2236100 | 100 | 0 | 1895000 | 341100 | 189500 | 2046600 | 0
23 | PQC, Peripheral road (~ 264m) | % | 100 | 47360 | 4736000 | 852480 | 5588480 | 100 | 0 | 4736000 | 852480 | 473600 | 5114880 | 0
24 | Shoulder, Peripheral road (~ 264m) | % | 100 | 6270 | 627000 | 112860 | 739860 |  | 100 | 0 | 0 | 0 | 0 | 627000
B | Drainage and harvesting pit
1 | Complete up to walls (CH 00.00 to CH 221.00) | % | 100 | 18940 | 1894000 | 340920 | 2234920 |  | 100 | 0 | 0 | 0 | 0 | 1894000
2 | Complete up to walls (CH 221.00 to CH 442.00) | % | 100 | 18940 | 1894000 | 340920 | 2234920 |  | 100 | 0 | 0 | 0 | 0 | 1894000
3 | Complete up to walls (CH 442.00 to CH 663.00) | % | 100 | 18940 | 1894000 | 340920 | 2234920 | 5.85 | 94.15 | 110799 | 19943.82 | 11079.9 | 119662.92 | 1783201
4 | Complete up to walls (CH 663.00 to CH 886.00) | % | 100 | 18940 | 1894000 | 340920 | 2234920 | 4.59 | 95.41 | 86934.6 | 15648.228 | 8693.46 | 93889.368 | 1807065.4
5 | Complete up to walls (Connecting roads to shed) | % | 100 | 18940 | 1894000 | 340920 | 2234920 |  | 100 | 0 | 0 | 0 | 0 | 1894000
6 | Complete up to walls (Peripheral road) | % | 100 | 18940 | 1894000 | 340920 | 2234920 | 87.12 | 12.88 | 1650052.8 | 297009.504 | 165005.28 | 1782057.024 | 243947.2
7 | Harvesting Pit | % | 100 | 12650 | 1265000 | 227700 | 1492700 |  | 100 | 0 | 0 | 0 | 0 | 1265000
C | Balance of plant foundations
1 | Foundation of Inert silo (Silo 1) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
2 | Silo Super Structure Inert silo (Silo 1) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
3 | Foundation of Inert silo (Silo 2) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
4 | Silo Super Structure Inert silo (Silo 2) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
5 | Foundation of Char silo (Silo 1) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
6 | Silo Super Structure Char silo (Silo 1) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
7 | Foundation of Char silo (Silo 2) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
8 | Silo Super Structure Char silo (Silo 2) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
9 | Chimney with Gas cleaning system foundations | % | 100 | 22100 | 2210000 | 397800 | 2607800 |  | 100 | 0 | 0 | 0 | 0 | 2210000
10 | Foundation of Air vent 1& 2 | % | 100 | 18800 | 1880000 | 338400 | 2218400 |  | 100 | 0 | 0 | 0 | 0 | 1880000
11 | LTP & ETP foundations & floor | % | 100 | 50500 | 5050000 | 909000 | 5959000 |  | 100 | 0 | 0 | 0 | 0 | 5050000
12 | Firefighting water storage tank foundations | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
13 | Firefighting pumps and other equipment foundations | % | 100 | 9480 | 948000 | 170640 | 1118640 |  | 100 | 0 | 0 | 0 | 0 | 948000
14 | Firefighting station floor | % | 100 | 6320 | 632000 | 113760 | 745760 |  | 100 | 0 | 0 | 0 | 0 | 632000
15 | Fire Pipe line foundation | % | 100 | 3160 | 316000 | 56880 | 372880 |  | 100 | 0 | 0 | 0 | 0 | 316000
16 | Foundation of weigh bridge | % | 100 | 47360 | 4736000 | 852480 | 5588480 | 20 | 80 | 947200 | 170496 | 94720 | 1022976 | 3788800
17 | DG set foundation | % | 100 | 6330 | 633000 | 113940 | 746940 |  | 100 | 0 | 0 | 0 | 0 | 633000
18 | Transformer foundation | % | 100 | 9500 | 950000 | 171000 | 1121000 |  | 100 | 0 | 0 | 0 | 0 | 950000
19 | Highmast light foundations | % | 100 | 25300 | 2530000 | 455400 | 2985400 | 100 | 0 | 2530000 | 455400 | 253000 | 2732400 | 0
D | Complete civil & finishing works of CMCS building
1 | Foundation up to plinth beam, including plinth beam | % | 100 | 63135 | 6313500 | 1136430 | 7449930 | 100 | 0 | 6313500 | 1136430 | 631350 | 6818580 | 0
2 | Earth back filling, trenches and GSB under floors | % | 100 | 63140 | 6314000 | 1136520 | 7450520 | 80.39 | 19.61 | 5075824.6 | 913648.428 | 507582.46 | 5481890.568 | 1238175.4
3 | Column, lintel Beams & including projections up to slab beam bottom level (GF) | % | 100 | 63135 | 6313500 | 1136430 | 7449930 | 100 | 0 | 6313500 | 1136430 | 631350 | 6818580 | 0
4 | Beams & Slab (GF) | % | 100 | 37890 | 3789000 | 682020 | 4471020 | 100 | 0 | 3789000 | 682020 | 378900 | 4092120 | 0
5 | Brickwork including openings (GF) | % | 100 | 47350 | 4735000 | 852300 | 5587300 |  | 100 | 0 | 0 | 0 | 0 | 4735000
6 | (Concealed) Plumbing and Sanitation (GF) | % | 100 | 9480 | 948000 | 170640 | 1118640 |  | 100 | 0 | 0 | 0 | 0 | 948000
7 | Inside plaster (GF) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
8 | Column, lintel Beams & including projections up to slab beam bottom level (FF) | % | 100 | 31570 | 3157000 | 568260 | 3725260 | 100 | 0 | 3157000 | 568260 | 315700 | 3409560 | 0
9 | Beams & Slab (FF) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
10 | Brickwork including openings (FF) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
11 | (Concealed) Plumbing and Sanitation (FF) | % | 100 | 31575 | 3157500 | 568350 | 3725850 |  | 100 | 0 | 0 | 0 | 0 | 3157500
12 | Inside plaster (FF) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
13 | Fixing of doors and windows | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
14 | Fixing of all sanitary items in toilets | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
15 | Flooring and tiling (GF) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
16 | Flooring and tiling (FF) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
17 | Outside plastering | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
18 | Inside finishing (GF) | % | 100 | 15785 | 1578500 | 284130 | 1862630 |  | 100 | 0 | 0 | 0 | 0 | 1578500
19 | Inside finishing (FF) | % | 100 | 15785 | 1578500 | 284130 | 1862630 |  | 100 | 0 | 0 | 0 | 0 | 1578500
20 | Outside finishing | % | 100 | 15785 | 1578500 | 284130 | 1862630 |  | 100 | 0 | 0 | 0 | 0 | 1578500
21 | Terrace water proofing, screed concrete & fixing of traps for rain water pipes | % | 100 | 3160 | 316000 | 56880 | 372880 |  | 100 | 0 | 0 | 0 | 0 | 316000
21 | Plinth protection & Drain with cover | % | 100 | 6320 | 632000 | 113760 | 745760 |  | 100 | 0 | 0 | 0 | 0 | 632000
E | Complete civil & finishing works of main plant shed
1 | Raft of MSW pit | % | 100 | 157850 | 15785000 | 2841300 | 18626300 | 25 | 75 | 3946250 | 710325 | 394625 | 4261950 | 11838750
2 | Walls of MSW pit | % | 100 | 126280 | 12628000 | 2273040 | 14901040 |  | 100 | 0 | 0 | 0 | 0 | 12628000
3 | Water proofing / Apoxy Painting of MSW pit | % | 100 | 6320 | 632000 | 113760 | 745760 |  | 100 | 0 | 0 | 0 | 0 | 632000
4 | Foundations and pedestal of shed including foundation bolt (Zone A) | % | 100 | 63150 | 6315000 | 1136700 | 7451700 |  | 100 | 0 | 0 | 0 | 0 | 6315000
5 | Foundations and pedestal of shed including foundation bolt (Zone B) | % | 100 | 63150 | 6315000 | 1136700 | 7451700 | 50 | 50 | 3157500 | 568350 | 315750 | 3410100 | 3157500
6 | Foundations and pedestal of shed including foundation bolt (Zone C) | % | 100 | 63150 | 6315000 | 1136700 | 7451700 | 66.17 | 33.83 | 4178635.5 | 752154.39 | 417863.55 | 4512926.34 | 2136364.5
7 | Plinth beam (Zone A) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
8 | Plinth beam (Zone B) | % | 100 | 15790 | 1579000 | 284220 | 1863220 | 44.48 | 55.52 | 702339.2 | 126421.056 | 70233.92 | 758526.336 | 876660.8
9 | Plinth beam (Zone C) | % | 100 | 15790 | 1579000 | 284220 | 1863220 | 47.06 | 52.94 | 743077.4 | 133753.932 | 74307.74 | 802523.592 | 835922.6
10 | Grade slab and flooring (Zone A) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
11 | Grade slab and flooring (Zone B) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
12 | Grade slab and flooring (Zone C) | % | 100 | 31570 | 3157000 | 568260 | 3725260 |  | 100 | 0 | 0 | 0 | 0 | 3157000
13 | Parapet & Plinth protection | % | 100 | 12630 | 1263000 | 227340 | 1490340 |  | 100 | 0 | 0 | 0 | 0 | 1263000
14 | Shed peripheral drain with cover | % | 100 | 18940 | 1894000 | 340920 | 2234920 |  | 100 | 0 | 0 | 0 | 0 | 1894000
F | Individual equipment foundations inside the main plant shed
1 | Foundation of MSW Hopper (3 Sets) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
2 | Foundation of Drum Dryer (3 Sets) | % | 100 | 63120 | 6312000 | 1136160 | 7448160 |  | 100 | 0 | 0 | 0 | 0 | 6312000
3 | Foundation of MSW Conveyor (3 Sets) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
4 | Foundation of Ballistic Separator (3 Sets) | % | 100 | 31580 | 3158000 | 568440 | 3726440 |  | 100 | 0 | 0 | 0 | 0 | 3158000
5 | Foundation of Shredder Conveyor (3 Sets) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
6 | Foundation of Shredder (3 Sets) | % | 100 | 31580 | 3158000 | 568440 | 3726440 |  | 100 | 0 | 0 | 0 | 0 | 3158000
7 | Foundation of RDF Conveyor (3 Sets) | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
8 | Foundation of RDF Hopper (3 Sets) | % | 100 | 47370 | 4737000 | 852660 | 5589660 |  | 100 | 0 | 0 | 0 | 0 | 4737000
9 | Foundation of Reactor (3 Sets) | % | 100 | 94740 | 9474000 | 1705320 | 11179320 | 100 | 0 | 9474000 | 1705320 | 947400 | 10231920 | 0
10 | Air compressor foundation | % | 100 | 15750 | 1575000 | 283500 | 1858500 |  | 100 | 0 | 0 | 0 | 0 | 1575000
11 | Misc. Civil Works |  | 100 | 31580 | 3158000 | 568440 | 3726440 |  | 100 | 0 | 0 | 0 | 0 | 3158000
G | Complete civil & finishing works of all other buildings
1 | Rest room and toilet | % | 100 | 31572 | 3157200 | 568296 | 3725496 | 75 | 25 | 2367900 | 426222 | 236790 | 2557332 | 789300
2 | Security rooms | % | 100 | 15790 | 1579000 | 284220 | 1863220 | 85 | 15 | 1342150 | 241587 | 134215 | 1449522 | 236850
3 | Car parking shed | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
4 | Area paving (Paver blocks) | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
H | Leacheat sump & Cooling Tower foundation | [9 empty] | 0
1 | Raft, Wall and covers | % | 100 | 3157 | 315700 | 56826 | 372526 |  | 100 | 0 | 0 | 0 | 0 | 315700
2 | Cooling Tower Foundation | % | 100 | 15785 | 1578500 | 284130 | 1862630 |  | 100 | 0 | 0 | 0 | 0 | 1578500
I | Earth filling & area development | % | 100 | 296675 | 29667500 | 5340150 | 35007650 |  | 100 | 0 | 0 | 0 | 0 | 29667500
J | Horticulture with fountain
1 | Plantations of trees | % | 100 | 6310 | 631000 | 113580 | 744580 |  | 100 | 0 | 0 | 0 | 0 | 631000
2 | Plantation of bushes | % | 100 | 3160 | 316000 | 56880 | 372880 |  | 100 | 0 | 0 | 0 | 0 | 316000
3 | Plantation of grasses | % | 100 | 3160 | 316000 | 56880 | 372880 |  | 100 | 0 | 0 | 0 | 0 | 316000
4 | Fountain | % | 100 | 3160 | 316000 | 56880 | 372880 |  | 100 | 0 | 0 | 0 | 0 | 316000
C | Site Fabricated Steel Structure
i | Supply , Fabrication, & erection of site fabricated steel structure works | Lot | 1 | 40000000 | 40000000 | 7200000 | 47200000 |  | 1 | 0 | 0 | 0 | 0 | 40000000
D | Training Charges | Lot | 1 | 300000 | 300000 | 54000 | 354000 |  | 1 | 0 | 0 | 0 | 0 | 300000
6 | Amount Linked to Safety Aspects | Lot | 1 | 2500000 | 2500000 | 450000 | 2950000 |  | 1 | 0 | 0 | 0 | 0 | 2500000

## Hubballi_EPC Package_SC
Payments Status Hubballi Project: EPC Package
S. No. | Service | AS per PO and BBU | [10 empty] | Total Payment incl GST |  | Remarks
|  | UOM | QTY | UNIT RATE | PO Amount | GST Amount as per PO | Total Amount incl GST as per PO | Billed QTY | Balance QTY | Bill Amount | GST Amount | Sucessful Completion of PG Test for Entire EPC Package |  | Balance Amount
10%
II | EPC Package_SC AS per PO No. 5500045014-109-2C05 dated 13.08.2024 |  |  |  | 349506520 | 62911173.6 | 412417693.6 |  |  | 113636287.45 | 20454531.741 | 11363628.745 | 122727190.446 | 235870232.55 |  | 278326874.409
1 | Local Transportation including port clearance and port charges and Inland insurance charges for Main Equipments | Set | 1 | 5000000 | 5000000 | 900000 | 5900000 | 0 | 1 | 0 | 0 | 0 | 0 | 5000000
Installation Services for Main Equipment excluding factory Fabricated Structures
EQUIPMENT FOR MAIN PLANT
2 | Main Equipment excluding Factory Fabricated Steel Structure | Lot | 1 | 38544920 | 38544920 | 6938085.6 | 45483005.6 | 0 | 1 | 0 | 0 | 0 | 0 | 38544920
3 | Erection of Factory Fabricated Steel Structures | Lot | 1 | 10000000 | 10000000 | 1800000 | 11800000 | 0 | 1 | 0 | 0 | 0 | 0 | 10000000
4 | Civil, Structure & Architectural Works
A | Roads with shoulder
1 | GSB & WMM (CH 00.00 to CH 193.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
2 | DLC (CH 00.00 to CH 193.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
3 | PQC (CH 00.00 to CH 193.00) | % | 100 | 39500 | 3950000 | 711000 | 4661000 | 100 | 0 | 3950000 | 711000 | 395000 | 4266000 | 0
4 | Shoulder (CH 00.00 to CH 193.00) | % | 100 | 5260 | 526000 | 94680 | 620680 | 78 | 22 | 410280 | 73850.4 | 41028 | 443102.4 | 115720
5 | GSB & WMM (CH 193.00 to CH 385.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
6 | DLC (CH 193.00 to CH 385.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
7 | PQC (CH 193.00 to CH 385.00) | % | 100 | 39500 | 3950000 | 711000 | 4661000 | 100 | 0 | 3950000 | 711000 | 395000 | 4266000 | 0
8 | Shoulder (CH 193.00 to CH 385.00) | % | 100 | 5260 | 526000 | 94680 | 620680 | 44.2 | 55.8 | 232492 | 41848.56 | 23249.2 | 251091.36 | 293508
9 | GSB & WMM (CH 385.00 to CH 578.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
10 | DLC (CH 385.00 to CH 578.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
11 | PQC (CH 385.00 to CH 578.00) | % | 100 | 39500 | 3950000 | 711000 | 4661000 | 100 | 0 | 3950000 | 711000 | 395000 | 4266000 | 0
12 | Shoulder (CH 385.00 to CH 578.00) | % | 100 | 5260 | 526000 | 94680 | 620680 | 88.4 | 11.6 | 464984 | 83697.12 | 46498.4 | 502182.72 | 61016
13 | GSB & WMM (CH 578.00 to CH 771.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
14 | DLC (CH 578.00 to CH 771.00) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 100 | 0 | 2631000 | 473580 | 263100 | 2841480 | 0
15 | PQC (CH 578.00 to CH 771.00) | % | 100 | 39500 | 3950000 | 711000 | 4661000 | 100 | 0 | 3950000 | 711000 | 395000 | 4266000 | 0
16 | Shoulder (CH 578.00 to CH 771.00) | % | 100 | 5260 | 526000 | 94680 | 620680 | 47.84 | 52.16 | 251638.4 | 45294.912 | 25163.84 | 271769.472 | 274361.6
17 | GSB & WMM, Connecting roads to shed (~ 89m) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
18 | DLC, Connecting roads to shed (~ 89m) | % | 100 | 10530 | 1053000 | 189540 | 1242540 |  | 100 | 0 | 0 | 0 | 0 | 1053000
19 | PQC, Connecting roads to shed (~ 89m) | % | 100 | 26320 | 2632000 | 473760 | 3105760 |  | 100 | 0 | 0 | 0 | 0 | 2632000
20 | Shoulder Connecting roads to shed (~ 89m) | % | 100 | 2630 | 263000 | 47340 | 310340 |  | 100 | 0 | 0 | 0 | 0 | 263000
B | Drainage and harvesting pit | [9 empty] | 0
1 | Complete up to walls (CH 00.00 to CH 235.00) | % | 100 | 18420 | 1842000 | 331560 | 2173560 | 63.83 | 36.17 | 1175748.6 | 211634.748 | 117574.86 | 1269808.488 | 666251.4
2 | Complete up to walls (CH 235.00 to CH 470.00) | % | 100 | 18420 | 1842000 | 331560 | 2173560 | 55.32 | 44.68 | 1018994.4 | 183418.992 | 101899.44 | 1100513.952 | 823005.6
3 | Complete up to walls (CH 470.00 to CH 705.00) | % | 100 | 18420 | 1842000 | 331560 | 2173560 | 55.32 | 44.68 | 1018994.4 | 183418.992 | 101899.44 | 1100513.952 | 823005.6
4 | Complete up to walls (CH 705.00 to CH 940.00) | % | 100 | 18420 | 1842000 | 331560 | 2173560 |  | 100 | 0 | 0 | 0 | 0 | 1842000
5 | Complete up to walls (Connecting roads to shed) | % | 100 | 18420 | 1842000 | 331560 | 2173560 |  | 100 | 0 | 0 | 0 | 0 | 1842000
6 | Harvesting Pit | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
C | Balance of plant foundations
1 | Foundation of Inert silo (Silo 1) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
2 | Silo Super Structure Inert silo (Silo 1) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
3 | Foundation of Inert silo (Silo 2) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
4 | Silo Super Structure Inert silo (Silo 2) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
5 | Foundation of Char silo (Silo 1) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 30 | 70 | 789300 | 142074 | 78930 | 852444 | 1841700
6 | Silo Super Structure Char silo (Silo 1) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
7 | Foundation of Char silo (Silo 2) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
8 | Silo Super Structure Char silo (Silo 2) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
9 | Chimney with Gas cleaning system foundations | % | 100 | 18420 | 1842000 | 331560 | 2173560 | 30 | 70 | 552600 | 99468 | 55260 | 596808 | 1289400
10 | Foundation of Air vent | % | 100 | 7900 | 790000 | 142200 | 932200 |  | 100 | 0 | 0 | 0 | 0 | 790000
11 | LTP & ETP foundations & floor | % | 100 | 42100 | 4210000 | 757800 | 4967800 |  | 100 | 0 | 0 | 0 | 0 | 4210000
12 | Firefighting water storage tank foundations | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
13 | Firefighting pumps and other equipment foundations | % | 100 | 7890 | 789000 | 142020 | 931020 |  | 100 | 0 | 0 | 0 | 0 | 789000
14 | Firefighting station floor | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
15 | Fire Pipe line foundation | % | 100 | 2630 | 263000 | 47340 | 310340 |  | 100 | 0 | 0 | 0 | 0 | 263000
16 | Foundation of weigh bridge | % | 100 | 39480 | 3948000 | 710640 | 4658640 | 80.04 | 19.96 | 3159979.2 | 568796.256 | 315997.92 | 3412777.536 | 788020.8
17 | DG set foundation | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
18 | Transformer foundation | % | 100 | 7890 | 789000 | 142020 | 931020 |  | 100 | 0 | 0 | 0 | 0 | 789000
19 | Highmast light foundations | % | 100 | 21050 | 2105000 | 378900 | 2483900 | 100 | 0 | 2105000 | 378900 | 210500 | 2273400 | 0
D | Complete civil & finishing works of CMCS building
1 | Foundation up to plinth beam, including plinth beam | % | 100 | 52655 | 5265500 | 947790 | 6213290 | 100 | 0 | 5265500 | 947790 | 526550 | 5686740 | 0
2 | Earth back filling, trenches and GSB under floors | % | 100 | 52620 | 5262000 | 947160 | 6209160 | 100 | 0 | 5262000 | 947160 | 526200 | 5682960 | 0
3 | Column, lintel Beams & including projections up to slab beam bottom level (GF) | % | 100 | 52655 | 5265500 | 947790 | 6213290 | 90.11 | 9.89 | 4744742.05 | 854053.569 | 474474.205 | 5124321.414 | 520757.95
4 | Beams & Slab (GF) | % | 100 | 31580 | 3158000 | 568440 | 3726440 |  | 100 | 0 | 0 | 0 | 0 | 3158000
5 | Brickwork including openings (GF) | % | 100 | 39500 | 3950000 | 711000 | 4661000 |  | 100 | 0 | 0 | 0 | 0 | 3950000
6 | (Concealed) Plumbing and Sanitation (GF) | % | 100 | 7890 | 789000 | 142020 | 931020 |  | 100 | 0 | 0 | 0 | 0 | 789000
7 | Inside plaster (GF) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
8 | Column, lintel Beams & including projections up to slab beam bottom level (FF) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
9 | Beams & Slab (FF) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
10 | Brickwork including openings (FF) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
11 | (Concealed) Plumbing and Sanitation (FF) | % | 100 | 26345 | 2634500 | 474210 | 3108710 |  | 100 | 0 | 0 | 0 | 0 | 2634500
12 | Inside plaster (FF) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
13 | Fixing of doors and windows | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
14 | Fixing of all sanitary items in toilets | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
15 | Flooring and tiling (GF) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
16 | Flooring and tiling (FF) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
17 | Outside plastering | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
18 | Inside finishing (GF) | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
19 | Inside finishing (FF) | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
20 | Outside finishing | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
21 | Terrace water proofing, screed concrete & fixing of traps for rain water pipes | % | 100 | 2630 | 263000 | 47340 | 310340 |  | 100 | 0 | 0 | 0 | 0 | 263000
22 | Plinth protection & Drain with cover | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
E | Complete civil & finishing works of main plant shed
1 | Raft of MSW pit | % | 100 | 131580 | 13158000 | 2368440 | 15526440 | 100 | 0 | 13158000 | 2368440 | 1315800 | 14210640 | 0
2 | Walls of MSW pit | % | 100 | 105270 | 10527000 | 1894860 | 12421860 | 80 | 20 | 8421600 | 1515888 | 842160 | 9095328 | 2105400
3 | Water proofing / Apoxy Painting of MSW pit | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
4 | Foundations and pedestal of shed including foundation bolt (Zone A) | % | 100 | 52630 | 5263000 | 947340 | 6210340 | 90.48 | 9.52 | 4761962.4 | 857153.232 | 476196.24 | 5142919.392 | 501037.6
5 | Foundations and pedestal of shed including foundation bolt (Zone B) | % | 100 | 52630 | 5263000 | 947340 | 6210340 | 90 | 10 | 4736700 | 852606 | 473670 | 5115636 | 526300
6 | Foundations and pedestal of shed including foundation bolt (Zone C) | % | 100 | 52630 | 5263000 | 947340 | 6210340 | 29.4 | 70.6 | 1547322 | 278517.96 | 154732.2 | 1671107.76 | 3715678
7 | Plinth beam (Zone A) | % | 100 | 13160 | 1316000 | 236880 | 1552880 | 100 | 0 | 1316000 | 236880 | 131600 | 1421280 | 0
8 | Plinth beam (Zone B) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
9 | Plinth beam (Zone C) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
10 | Grade slab and flooring (Zone A) | % | 100 | 26310 | 2631000 | 473580 | 3104580 | 30 | 70 | 789300 | 142074 | 78930 | 852444 | 1841700
11 | Grade slab and flooring (Zone B) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
12 | Grade slab and flooring (Zone C) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
13 | Parapet & Plinth protection | % | 100 | 10530 | 1053000 | 189540 | 1242540 |  | 100 | 0 | 0 | 0 | 0 | 1053000
14 | Shed peripheral drain with cover | % | 100 | 15790 | 1579000 | 284220 | 1863220 |  | 100 | 0 | 0 | 0 | 0 | 1579000
F | Individual equipment foundations inside the main plant shed
1 | Foundation of MSW Hopper (2 Sets) | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
2 | Foundation of Drum Dryer (2 Sets) | % | 100 | 52620 | 5262000 | 947160 | 6209160 |  | 100 | 0 | 0 | 0 | 0 | 5262000
3 | Foundation of MSW Conveyor (2 Sets) | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
4 | Foundation of Ballistic Separator (2 Sets) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
5 | Foundation of Shredder Conveyor (2 Sets) | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
6 | Foundation of Shredder (2 Sets) | % | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
7 | Foundation of RDF Conveyor (2 Sets) | % | 100 | 13155 | 1315500 | 236790 | 1552290 |  | 100 | 0 | 0 | 0 | 0 | 1315500
8 | Foundation of RDF Hopper (2 Sets) | % | 100 | 52620 | 5262000 | 947160 | 6209160 | 30 | 70 | 1578600 | 284148 | 157860 | 1704888 | 3683400
9 | Foundation of Reactor (2 Sets) | % | 100 | 78930 | 7893000 | 1420740 | 9313740 | 100 | 0 | 7893000 | 1420740 | 789300 | 8524440 | 0
10 | Air compressor foundation | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
11 | Misc. Civil Works |  | 100 | 26310 | 2631000 | 473580 | 3104580 |  | 100 | 0 | 0 | 0 | 0 | 2631000
G | Complete civil & finishing works of all other buildings
1 | Rest room and toilet | % | 100 | 26320 | 2632000 | 473760 | 3105760 | 50 | 50 | 1316000 | 236880 | 131600 | 1421280 | 1316000
2 | Security rooms | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
3 | Car parking shed | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
4 | Area paving (Paver blocks) | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
H | Leacheat sump & Cooling Tower foundation
1 | Raft, Wall and covers | % | 100 | 2630 | 263000 | 47340 | 310340 | 80 | 20 | 210400 | 37872 | 21040 | 227232 | 52600
2 | Cooling Tower Foundation | % | 100 | 7890 | 789000 | 142020 | 931020 |  | 100 | 0 | 0 | 0 | 0 | 789000
I | Boundary wall with gates
1 | Foundations up to and including plinth beam (Side 1) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
2 | Super structure Column, beam and coping beam (Side1) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
3 | Both side plastering (Side 1) | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
4 | Foundations up to and including plinth beam (Side 2) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
5 | Super structure Column, beam and coping beam (Side 2) | % | 100 | 13160 | 1316000 | 236880 | 1552880 |  | 100 | 0 | 0 | 0 | 0 | 1316000
6 | Both side plastering (Side 2) | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
J | Earth Filling & area development | % | 100 | 184286 | 18428600 | 3317148 | 21745748 | 25 | 75 | 4607150 | 829287 | 460715 | 4975722 | 13821450
K | Horticulture with fountain
1 | Plantations of trees | % | 100 | 5260 | 526000 | 94680 | 620680 |  | 100 | 0 | 0 | 0 | 0 | 526000
2 | Plantation of bushes | % | 100 | 2630 | 263000 | 47340 | 310340 |  | 100 | 0 | 0 | 0 | 0 | 263000
3 | Plantation of grasses | % | 100 | 2630 | 263000 | 47340 | 310340 |  | 100 | 0 | 0 | 0 | 0 | 263000
4 | Fountain | % | 100 | 2630 | 263000 | 47340 | 310340 |  | 100 | 0 | 0 | 0 | 0 | 263000
5 | Site Fabricated Steel Structure
i | Supply , Fabrication, & erection of site fabricated steel structure works | Lot | 1 | 30000000 | 30000000 | 5400000 | 35400000 |  | 1 | 0 | 0 | 0 | 0 | 30000000
6 | Training Charges | Lot | 1 | 300000 | 300000 | 54000 | 354000 |  | 1 | 0 | 0 | 0 | 0 | 300000
7 | Amount Linked to Safety Aspects | Lot | 1 | 2500000 | 2500000 | 450000 | 2950000 |  | 1 | 0 | 0 | 0 | 0 | 2500000

## Noida_EPC Package_SC
Payments Status NOIDA Project: EPC Package
S. No. | Service | AS per PO and BBU | [10 empty] | Total Payment incl GST |  | Remarks
|  | UOM | QTY | UNIT RATE | PO Amount | GST Amount as per PO | Total Amount incl GST as per PO | Billed QTY | Balance QTY | Bill Amount | GST Amount | Sucessful Completion of PG Test for Entire EPC Package |  | Balance Amount
10%
II | EPC Package_SC AS per PO No. 5500044305-109-2C04 |  |  |  | 562415950 | 101234871 | 663650821 |  |  | 26130889.8 | 3606062.7924 | 2613088.98 | 27123863.6124 | 536285060.2 |  | 632816371.036
1 | Local Transportation including port clearance and port charges and Inland insurance charges for Main Equipments | Set | 1 | 5000000 | 5000000 | 900000 | 5900000 | 0 | 1 | 0 | 0 | 0 | 0 | 5000000
Installation Services for Main Equipment excluding factory Fabricated Structures
EQUIPMENT FOR MAIN PLANT
2 | Main Equipment excluding Factory Fabricated Steel Structure | Lot | 1 | 64835950 | 64835950 | 11670471 | 76506421 | 0 | 1 | 0 | 0 | 0 | 0 | 64835950
3 | Erection of Factory Fabricated Steel Structures | Lot | 1 | 15000000 | 15000000 | 2700000 | 17700000 | 0 | 1 | 0 | 0 | 0 | 0 | 15000000
4 | Civil, Structure & Architectural Works
A | Roads with shoulder
1 | GSB & WMM (CH 00.00 to CH 235.00) | % | 100 | 30440 | 3044000 | 547920 | 3591920 | 65.96 | 34.04 | 2007822.4 | 277079.4912 | 200782.24 | 2084119.6512 | 1036177.6
2 | DLC (CH 00.00 to CH 235.00) | % | 100 | 26090 | 2609000 | 469620 | 3078620 | 31.91 | 68.09 | 832531.9 | 114889.4022 | 83253.19 | 864168.1122 | 1776468.1
3 | PQC (CH 00.00 to CH 235.00) | % | 100 | 65220 | 6522000 | 1173960 | 7695960 |  | 100 | 0 | 0 | 0 | 0 | 6522000
4 | Shoulder (CH 00.00 to CH 235.00) | % | 100 | 8680 | 868000 | 156240 | 1024240 |  | 100 | 0 | 0 | 0 | 0 | 868000
5 | GSB & WMM (CH 235.00 to CH 470.00) | % | 100 | 30440 | 3044000 | 547920 | 3591920 | 55.31 | 44.69 | 1683636.4 | 232341.8232 | 168363.64 | 1747614.5832 | 1360363.6
6 | DLC (CH 235.00 to CH 470.00) | % | 100 | 26090 | 2609000 | 469620 | 3078620 | 23.4 | 76.6 | 610506 | 84249.828 | 61050.6 | 633705.228 | 1998494
7 | PQC (CH 235.00 to CH 470.00) | % | 100 | 65220 | 6522000 | 1173960 | 7695960 |  | 100 | 0 | 0 | 0 | 0 | 6522000
8 | Shoulder (CH 235.00 to CH 470.00) | % | 100 | 8680 | 868000 | 156240 | 1024240 |  | 100 | 0 | 0 | 0 | 0 | 868000
9 | GSB & WMM (CH 470.00 to CH 705.00) | % | 100 | 30440 | 3044000 | 547920 | 3591920 |  | 100 | 0 | 0 | 0 | 0 | 3044000
10 | DLC GSB & WMM (CH 470.00 to CH 705.00) | % | 100 | 26090 | 2609000 | 469620 | 3078620 |  | 100 | 0 | 0 | 0 | 0 | 2609000
11 | PQC GSB & WMM (CH 470.00 to CH 705.00) | % | 100 | 65220 | 6522000 | 1173960 | 7695960 |  | 100 | 0 | 0 | 0 | 0 | 6522000
12 | Shoulder GSB & WMM (CH 470.00 to CH 705.00) | % | 100 | 8680 | 868000 | 156240 | 1024240 |  | 100 | 0 | 0 | 0 | 0 | 868000
13 | GSB & WMM (CH 705.00 to CH 940.00) | % | 100 | 30440 | 3044000 | 547920 | 3591920 | 76.6 | 23.4 | 2331704 | 321775.152 | 233170.4 | 2420308.752 | 712296
14 | DLC (CH 705.00 to CH 940.00) | % | 100 | 26090 | 2609000 | 469620 | 3078620 | 76.6 | 23.4 | 1998494 | 275792.172 | 199849.4 | 2074436.772 | 610506
15 | PQC (CH 705.00 to CH 940.00) | % | 100 | 65220 | 6522000 | 1173960 | 7695960 | 26.81 | 73.19 | 1748548.2 | 241299.6516 | 174854.82 | 1814993.0316 | 4773451.8
16 | Shoulder (CH 705.00 to CH 940.00) | % | 100 | 8680 | 868000 | 156240 | 1024240 |  | 100 | 0 | 0 | 0 | 0 | 868000
17 | GSB & WMM, Connecting roads to shed (~ 222m) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
18 | DLC, Connecting roads to shed (~ 222m) | % | 100 | 17390 | 1739000 | 313020 | 2052020 |  | 100 | 0 | 0 | 0 | 0 | 1739000
19 | PQC, Connecting roads to shed (~ 222m) | % | 100 | 34780 | 3478000 | 626040 | 4104040 |  | 100 | 0 | 0 | 0 | 0 | 3478000
20 | Shoulder Connecting roads to shed (~ 222m) | % | 100 | 4350 | 435000 | 78300 | 513300 |  | 100 | 0 | 0 | 0 | 0 | 435000
21 | GSB & WMM, Peripheral road (~ 572m) | % | 100 | 30440 | 3044000 | 547920 | 3591920 | 87.41 | 12.59 | 2660760.4 | 367184.9352 | 266076.04 | 2761869.2952 | 383239.6
22 | DLC, Peripheral road (~ 572m) | % | 100 | 26090 | 2609000 | 469620 | 3078620 | 87.41 | 12.59 | 2280526.9 | 314712.7122 | 228052.69 | 2367186.9222 | 328473.1
23 | PQC, Peripheral road (~ 572m) | % | 100 | 65220 | 6522000 | 1173960 | 7695960 | 27.97 | 72.03 | 1824203.4 | 251740.0692 | 182420.34 | 1893523.1292 | 4697796.6
24 | Shoulder, Peripheral road (~ 572m) | % | 100 | 8680 | 868000 | 156240 | 1024240 |  | 100 | 0 | 0 | 0 | 0 | 868000
B | Drainage and harvesting pit
1 | Complete up to walls (CH 00.00 to CH 235.00) | % | 100 | 30430 | 3043000 | 547740 | 3590740 |  | 100 | 0 | 0 | 0 | 0 | 3043000
2 | Complete up to walls (CH 235.00 to CH 470.00) | % | 100 | 30430 | 3043000 | 547740 | 3590740 |  | 100 | 0 | 0 | 0 | 0 | 3043000
3 | Complete up to walls (CH 470.00 to CH 705.00) | % | 100 | 30430 | 3043000 | 547740 | 3590740 |  | 100 | 0 | 0 | 0 | 0 | 3043000
4 | Complete up to walls (CH 705.00 to CH 940.00) | % | 100 | 30430 | 3043000 | 547740 | 3590740 |  | 100 | 0 | 0 | 0 | 0 | 3043000
5 | Complete up to walls (Connecting roads to shed) | % | 100 | 30430 | 3043000 | 547740 | 3590740 |  | 100 | 0 | 0 | 0 | 0 | 3043000
6 | Complete up to walls (Peripheral road) | % | 100 | 30430 | 3043000 | 547740 | 3590740 |  | 100 | 0 | 0 | 0 | 0 | 3043000
| Harvesting Pit | % | 100 | 26100 | 2610000 | 469800 | 3079800 |  | 100 | 0 | 0 | 0 | 0 | 2610000
C | Balance of plant foundations
1 | Foundation of Inert silo (Silo 1) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
2 | Silo Super Structure Inert silo (Silo 1) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
3 | Foundation of Inert silo (Silo 2) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
4 | Silo Super Structure Inert silo (Silo 2) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
5 | Foundation of Char silo (Silo 1) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
6 | Silo Super Structure Char silo (Silo 1) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
7 | Foundation of Char silo (Silo 2) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
8 | Silo Super Structure Char silo (Silo 2) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
9 | Chimney with Gas cleaning system foundations | % | 100 | 60870 | 6087000 | 1095660 | 7182660 |  | 100 | 0 | 0 | 0 | 0 | 6087000
10 | Foundation of Air vent 1 & 2 | % | 100 | 26080 | 2608000 | 469440 | 3077440 |  | 100 | 0 | 0 | 0 | 0 | 2608000
11 | LTP & ETP foundations & floor | % | 100 | 69560 | 6956000 | 1252080 | 8208080 |  | 100 | 0 | 0 | 0 | 0 | 6956000
12 | Firefighting water storage tank foundations | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
13 | Firefighting pumps and other equipment foundations | % | 100 | 13040 | 1304000 | 234720 | 1538720 |  | 100 | 0 | 0 | 0 | 0 | 1304000
14 | Firefighting station floor | % | 100 | 8700 | 870000 | 156600 | 1026600 |  | 100 | 0 | 0 | 0 | 0 | 870000
15 | Fire Pipe line foundation | % | 100 | 4340 | 434000 | 78120 | 512120 |  | 100 | 0 | 0 | 0 | 0 | 434000
16 | Foundation of weigh bridge | % | 100 | 65210 | 6521000 | 1173780 | 7694780 |  | 100 | 0 | 0 | 0 | 0 | 6521000
17 | DG set foundation | % | 100 | 8700 | 870000 | 156600 | 1026600 |  | 100 | 0 | 0 | 0 | 0 | 870000
18 | Transformer foundation | % | 100 | 13040 | 1304000 | 234720 | 1538720 |  | 100 | 0 | 0 | 0 | 0 | 1304000
19 | Highmast light foundations | % | 100 | 34780 | 3478000 | 626040 | 4104040 |  | 100 | 0 | 0 | 0 | 0 | 3478000
D | Complete civil & finishing works of CMCS building
1 | Foundation up to plinth beam, including plinth beam | % | 100 | 86950 | 8695000 | 1565100 | 10260100 | 34.38 | 65.62 | 2989341 | 412529.058 | 298934.1 | 3102935.958 | 5705659
2 | Earth back filling, trenches and GSB under floors | % | 100 | 86960 | 8696000 | 1565280 | 10261280 |  | 100 | 0 | 0 | 0 | 0 | 8696000
3 | Column, lintel Beams & including projections up to slab beam bottom level (GF) | % | 100 | 86950 | 8695000 | 1565100 | 10260100 |  | 100 | 0 | 0 | 0 | 0 | 8695000
4 | Beams & Slab (GF) | % | 100 | 52180 | 5218000 | 939240 | 6157240 |  | 100 | 0 | 0 | 0 | 0 | 5218000
5 | Brickwork including openings (GF) | % | 100 | 65210 | 6521000 | 1173780 | 7694780 |  | 100 | 0 | 0 | 0 | 0 | 6521000
6 | (Concealed) Plumbing and Sanitation (GF) | % | 100 | 13040 | 1304000 | 234720 | 1538720 |  | 100 | 0 | 0 | 0 | 0 | 1304000
7 | Inside plaster (GF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
8 | Column, lintel Beams & including projections up to slab beam bottom level (FF) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
9 | Beams & Slab (FF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
10 | Brickwork including openings (FF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
11 | (Concealed) Plumbing and Sanitation (FF) | % | 100 | 43470 | 4347000 | 782460 | 5129460 |  | 100 | 0 | 0 | 0 | 0 | 4347000
12 | Inside plaster (FF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
13 | Fixing of doors and windows | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
14 | Fixing of all sanitary items in toilets | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
15 | Flooring and tiling (GF) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
16 | Flooring and tiling (FF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
17 | Outside plastering | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
18 | Inside finishing (GF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
19 | Inside finishing (FF) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
20 | Outside finishing | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
21 | Terrace water proofing, screed concrete & fixing of traps for rain water pipes | % | 100 | 4350 | 435000 | 78300 | 513300 |  | 100 | 0 | 0 | 0 | 0 | 435000
22 | Plinth protection & Drain with cover | % | 100 | 8690 | 869000 | 156420 | 1025420 |  | 100 | 0 | 0 | 0 | 0 | 869000
E | Complete civil & finishing works of main plant shed
1 | Raft of MSW pit | % | 100 | 217400 | 21740000 | 3913200 | 25653200 |  | 100 | 0 | 0 | 0 | 0 | 21740000
2 | Walls of MSW pit | % | 100 | 173900 | 17390000 | 3130200 | 20520200 |  | 100 | 0 | 0 | 0 | 0 | 17390000
3 | Water proofing / Apoxy Painting of MSW pit | % | 100 | 8650 | 865000 | 155700 | 1020700 |  | 100 | 0 | 0 | 0 | 0 | 865000
4 | Foundations and pedestal of shed including foundation bolt (Zone A) | % | 100 | 86960 | 8696000 | 1565280 | 10261280 |  | 100 | 0 | 0 | 0 | 0 | 8696000
5 | Foundations and pedestal of shed including foundation bolt (Zone B) | % | 100 | 86960 | 8696000 | 1565280 | 10261280 |  | 100 | 0 | 0 | 0 | 0 | 8696000
6 | Foundations and pedestal of shed including foundation bolt (Zone C) | % | 100 | 86960 | 8696000 | 1565280 | 10261280 |  | 100 | 0 | 0 | 0 | 0 | 8696000
7 | Plinth beam (Zone A) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
8 | Plinth beam (Zone B) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
9 | Plinth beam (Zone C) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
10 | Grade slab and flooring (Zone A) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
11 | Grade slab and flooring (Zone B) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
12 | Grade slab and flooring (Zone C) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
13 | Parapet & Plinth protection | % | 100 | 17400 | 1740000 | 313200 | 2053200 |  | 100 | 0 | 0 | 0 | 0 | 1740000
14 | Shed peripheral drain with cover | % | 100 | 26090 | 2609000 | 469620 | 3078620 |  | 100 | 0 | 0 | 0 | 0 | 2609000
F | Individual equipment foundations inside the main plant shed
1 | Foundation of MSW Hopper (4 Sets) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
2 | Foundation of Drum Dryer (4 Sets) | % | 100 | 86960 | 8696000 | 1565280 | 10261280 |  | 100 | 0 | 0 | 0 | 0 | 8696000
3 | Foundation of MSW Conveyor (4 Sets) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
4 | Foundation of Ballistic Separator (4 Sets) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
5 | Foundation of Shredder Conveyor (4 Sets) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
6 | Foundation of Shredder (4 Sets) | % | 100 | 43480 | 4348000 | 782640 | 5130640 |  | 100 | 0 | 0 | 0 | 0 | 4348000
7 | Foundation of RDF Conveyor (4 Sets) | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
8 | Foundation of RDF Hopper (4 Sets) | % | 100 | 65220 | 6522000 | 1173960 | 7695960 |  | 100 | 0 | 0 | 0 | 0 | 6522000
9 | Foundation of Reactor (4 Sets) | % | 100 | 130440 | 13044000 | 2347920 | 15391920 | 39.58 | 60.42 | 5162815.2 | 712468.4976 | 516281.52 | 5359002.1776 | 7881184.8
10 | Air compressor foundation | % | 100 | 21700 | 2170000 | 390600 | 2560600 |  | 100 | 0 | 0 | 0 | 0 | 2170000
11 | Misc. Civil Works | % | 100 | 43440 | 4344000 | 781920 | 5125920 |  | 100 | 0 | 0 | 0 | 0 | 4344000
G | Complete civil & finishing works of all other buildings
1 | Rest room and toilet | % | 100 | 65210 | 6521000 | 1173780 | 7694780 |  | 100 | 0 | 0 | 0 | 0 | 6521000
2 | Security rooms | % | 100 | 43470 | 4347000 | 782460 | 5129460 |  | 100 | 0 | 0 | 0 | 0 | 4347000 |  | 10320
3 | Car parking shed | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
4 | Area paving (Paver blocks) | % | 100 | 21470 | 2147000 | 386460 | 2533460 |  | 100 | 0 | 0 | 0 | 0 | 2147000
H | Leacheat sump & Cooling Tower foundation
1 | Raft, Wall and covers | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
2 | Cooling Tower Foundation | % | 100 | 21740 | 2174000 | 391320 | 2565320 |  | 100 | 0 | 0 | 0 | 0 | 2174000
I | Earth filling & area development | % | 100 | 217820 | 21782000 | 3920760 | 25702760 |  | 100 | 0 | 0 | 0 | 0 | 21782000
J | Horticulture with fountain
1 | Plantations of trees | % | 100 | 13040 | 1304000 | 234720 | 1538720 |  | 100 | 0 | 0 | 0 | 0 | 1304000
2 | Plantation of bushes | % | 100 | 13040 | 1304000 | 234720 | 1538720 |  | 100 | 0 | 0 | 0 | 0 | 1304000
3 | Plantation of grasses | % | 100 | 13040 | 1304000 | 234720 | 1538720 |  | 100 | 0 | 0 | 0 | 0 | 1304000
4 | Fountain | % | 100 | 21720 | 2172000 | 390960 | 2562960 |  | 100 | 0 | 0 | 0 | 0 | 2172000
5 | Site Fabricated Steel Structure
i | Supply , Fabrication, & erection of site fabricated steel structure works | Lot | 1 | 40000000 | 40000000 | 7200000 | 47200000 |  | 1 | 0 | 0 | 0 | 0 | 40000000
6 | Training Charges | Lot | 1 | 300000 | 300000 | 54000 | 354000 |  | 1 | 0 | 0 | 0 | 0 | 300000
7 | Amount Linked to Safety Aspects | Lot | 1 | 2500000 | 2500000 | 450000 | 2950000 |  | 1 | 0 | 0 | 0 | 0 | 2500000

## Gorakhpur_EPC Package_SC
Payments Status Gorakhpur Project: EPC Package
S. No. | Service | AS per PO and BBU | [10 empty] | Total Payment incl GST |  | Remarks
|  | UOM | QTY | UNIT RATE | PO Amount | GST Amount as per PO | Total Amount incl GST as per PO | Billed QTY | Balance QTY | Bill Amount | GST Amount | Sucessful Completion of PG Test for Entire EPC Package |  | Balance Amount
10%
II | EPC Package_SC AS per PO No. 5500045014-109-2C05 dated 13.08.2024 |  |  |  | 444095593.848 | 61285191.951 | 505380785.799 | 29.17% |  | 129520701.3082 | 17873856.7805 | 12952070.1308 | 134442487.958 | 307738048.6898 |  | 363130897.4539
1 | Local Transportation including port clearance and port charges and Inland insurance charges for Main Equipments | Set | 1 | 9000000 | 9000000 | 1242000 | 10242000 | 0 | 1 | 0 | 0 | 0 | 0 | 9000000
2 | Installation Services for Main Equipment excluding factory Fabricated Structures
A | EQUIPMENT FOR MAIN PLANT
i | Main Equipment excluding Factory Fabricated Steel Structure | Lot | 1 | 51000000 | 51000000 | 7038000 | 58038000 | 0 | 1 | 0 | 0 | 0 | 0 | 51000000
ii | Erection of Factory Fabricated Steel Structures | Lot | 1 | 95000000 | 95000000 | 13110000 | 108110000 | 0 | 1 | 0 | 0 | 0 | 0 | 95000000
B | Civil, Structure & Architectural Works | Lot | 1 | [12 empty] | 106196735.791
a | SITE INVESTIGATION AND PREPARATION
1 | Topographical survey | Lot | 1 | 1000000 | 1000000 | 138000 | 1138000 | 1 | 0 | 1000000 | 138000 | 100000 | 1038000 | 0
2 | AREA CLEARING, GRUBBING AND COMPACTION OF VIRGIN/ORIGINAL EARTH SURFACE | SQM | 36000 | 30 | 1080000 | 149040 | 1229040 | 36000 | 0 | 1080000 | 149040 | 108000 | 1121040 | 0
3 | Earth filling works | Cum | 73600 | 425 | 31280000 | 4316640 | 35596640 | 39447.12 | 34152.88 | 16765026 | 2313573.588 | 1676502.6 | 17402096.988 | 14514974
4 | Initial Test Pile completion | Nos | 6 | 166666.6667 | 1000000 | 138000 | 1138000 | 6 | 0 | 1000000 | 138000 | 100000 | 1038000 | 0
5 | Initial Test Pile Testing | Nos | 2 | 1000000 | 2000000 | 276000 | 2276000 | 2 | 0 | 2000000 | 276000 | 200000 | 2076000 | 0
6 | Construction of balance Existing Boundary Walls | RM | 95 | 2500 | 237500 | 32775 | 270275 | 95 | 0 | 237500 | 32775 | 23750 | 246525 | 0
7 | Construction of balance New Boundary Walls | RM | 400 | 2700 | 1080000 | 149040 | 1229040 | 150 | 250 | 405000 | 55890 | 40500 | 420390 | 675000
8 | Plaster & painting of balance New Boundary Walls & Existing Boundary Walls | RM | 495 | 191 | 94545 | 13047.21 | 107592.21 | 0 | 495 | 0 | 0 | 0 | 0 | 94545
9 | Concertina Coil Fencing with Y angle | RM | 952 | 1055 | 1004360 | 138601.68 | 1142961.68 | 400 | 552 | 422000 | 58236 | 42200 | 438036 | 582360
10 | EMPLOYER FACILITIES | Lot | 1 | 1500000 | 1500000 | 207000 | 1707000 | 1 | 0 | 1500000 | 207000 | 150000 | 1557000 | 0
b | CIVIL WORKS FOR COMMON FACILITIES INCLUDING MSW PIT, CHIMNEY AND TRUCK BAY | Lot | 1 | 57500000
B1 | WET ESP Work Foundation | Sets | 1
B1.1 | Excavation | % | 20 | 70000 | 1400000 | 193200 | 1593200 | 20 | 0 | 1400000 | 193200 | 140000 | 1453200 | 0
B1.2 | RCC for Foundation up- Raft including Tie beam if any | % | 40 | 70000 | 2800000 | 386400 | 3186400 | 40 | 0 | 2800000 | 386400 | 280000 | 2906400 | 0
B1.3 | RCC Column/Pedestal above Raft to Bolt level | % | 40 | 70000 | 2800000 | 386400 | 3186400 | 40 | 0 | 2800000 | 386400 | 280000 | 2906400 | 0
B2 | ID Fan Foundation work | Sets | 2
B2.1 | GSB with metal soiling | % | 40 | 15000 | 600000 | 82800 | 682800 | 40 | 0 | 600000 | 82800 | 60000 | 622800 | 0
B2.2 | RCC for Foundation/Slab | % | 60 | 15000 | 900000 | 124200 | 1024200 | 60 | 0 | 900000 | 124200 | 90000 | 934200 | 0
B3 | FD Fan Foundation work | Sets | 2
B3.1 | GSB with metal soiling | % | 40 | 15000 | 600000 | 82800 | 682800 | 40 | 0 | 600000 | 82800 | 60000 | 622800 | 0
B3.2 | RCC for Foundation/Slab | % | 60 | 15000 | 900000 | 124200 | 1024200 | 60 | 0 | 900000 | 124200 | 90000 | 934200 | 0
B4 | TG Fan Foundation work | Sets | 2
B4.1 | GSB with metal soiling | % | 40 | 10000 | 400000 | 55200 | 455200 | 40 | 0 | 400000 | 55200 | 40000 | 415200 | 0
B4.2 | RCC for Foundation/Slab | % | 60 | 10000 | 600000 | 82800 | 682800 | 60 | 0 | 600000 | 82800 | 60000 | 622800 | 0
B5 | Cooling Tower Foundation work | Sets | 1
B5.1 | Excavation | % | 40 | 15000 | 600000 | 82800 | 682800 | 40 | 0 | 600000 | 82800 | 60000 | 622800 | 0
B5.2 | RCC for Foundation/Slab | % | 60 | 15000 | 900000 | 124200 | 1024200 | 60 | 0 | 900000 | 124200 | 90000 | 934200 | 0
B6 | Air Compressor, Air Dryer & reciver and Nitrogen Foundation work | Sets | 1
B6.1 | Excavation | % | 40 | 30000 | 1200000 | 165600 | 1365600 | 40 | 0 | 1200000 | 165600 | 120000 | 1245600 | 0
B6.2 | RCC for Foundation/Slab | % | 60 | 30000 | 1800000 | 248400 | 2048400 | 60 | 0 | 1800000 | 248400 | 180000 | 1868400 | 0
B7 | Chimney Foundation | Sets | 1
B7.1 | Pile | % | 40 | 50000 | 2000000 | 276000 | 2276000 | 40 | 0 | 2000000 | 276000 | 200000 | 2076000 | 0
B7.2 | Excavation | % | 10 | 50000 | 500000 | 69000 | 569000 | 10 | 0 | 500000 | 69000 | 50000 | 519000 | 0
B7.3 | Raft foundation | % | 40 | 50000 | 2000000 | 276000 | 2276000 | 40 | 0 | 2000000 | 276000 | 200000 | 2076000 | 0
B7.4 | Backfilling | % | 10 | 50000 | 500000 | 69000 | 569000 | 10 | 0 | 500000 | 69000 | 50000 | 519000 | 0
B8 | MSW PIT AREA CIVIL WORK | Sets | 1
B8.1 | Excavation | % | 15 | 290000 | 4350000 | 600300 | 4950300 | 11 | 4 | 3190000 | 440220 | 319000 | 3311220 | 1160000
B8.2 | RCC for PIT Raft | % | 30 | 290000 | 8700000 | 1200600 | 9900600 |  | 30 | 0 | 0 | 0 | 0 | 8700000
B8.3 | RCC Wall - 1st Lift | % | 15 | 290000 | 4350000 | 600300 | 4950300 |  | 15 | 0 | 0 | 0 | 0 | 4350000
B8.4 | RCC Wall - 2nd Lift | % | 20 | 290000 | 5800000 | 800400 | 6600400 |  | 20 | 0 | 0 | 0 | 0 | 5800000
B8.5 | RCC Wall - 3rd Lift | % | 20 | 290000 | 5800000 | 800400 | 6600400 |  | 20 | 0 | 0 | 0 | 0 | 5800000
B9 | MSW PIT Shed Foundation | Nos | 26
B9.1 | Excavation | % | 15 | 80000 | 1200000 | 165600 | 1365600 |  | 15 | 0 | 0 | 0 | 0 | 1200000
B9.2 | RCC for Foundation up- Raft including | % | 25 | 80000 | 2000000 | 276000 | 2276000 |  | 25 | 0 | 0 | 0 | 0 | 2000000
B9.3 | Tie beam | % | 25 | 80000 | 2000000 | 276000 | 2276000 |  | 25 | 0 | 0 | 0 | 0 | 2000000
B9.4 | RCC Column/Pedestal above Raft to Bolt level | % | 25 | 80000 | 2000000 | 276000 | 2276000 |  | 25 | 0 | 0 | 0 | 0 | 2000000
B9.5 | Back filling and compaction | % | 10 | 80000 | 800000 | 110400 | 910400 |  | 10 | 0 | 0 | 0 | 0 | 800000
c | CIVIL WORKS FOR PRE-PROCESSING, TORREFACTION AND POST PROCESSING FACILITIES | Lot | 1
C.1 | Exiting Shed Column civil foundation strengthening | Nos | 34 | [7 empty] | 0
C.1.1 | Exavation | % | 20 | 34000 | 680000 | 93840 | 773840 | 20 | 0 | 680000 | 93840 | 68000 | 705840 | 0
C.1.2 | RCC for Foundation - Raft | % | 40 | 34000 | 1360000 | 187680 | 1547680 | 40 | 0 | 1360000 | 187680 | 136000 | 1411680 | 0
C.1.3 | Back filling and compaction | % | 40 | 34000 | 1360000 | 187680 | 1547680 | 40 | 0 | 1360000 | 187680 | 136000 | 1411680 | 0
C.2 | Reactor foundation work for stream A,B,C | Sets | 3
C.2.1 | Exavation | % | 20 | 70000 | 1400000 | 193200 | 1593200 | 14 | 6 | 980000 | 135240 | 98000 | 1017240 | 420000
C.2.2 | RCC for Foundation up- Raft including Tie beam if any | % | 40 | 70000 | 2800000 | 386400 | 3186400 | 26 | 14 | 1820000 | 251160 | 182000 | 1889160 | 980000
C.2.3 | RCC Column/Pedestal above Raft to Bolt level | % | 40 | 70000 | 2800000 | 386400 | 3186400 | 18 | 22 | 1260000 | 173880 | 126000 | 1307880 | 1540000
C.3 | Drum dryer foundation work for stream A,B,C | Sets | 3
C.3.1 | Exavation | % | 20 | 35000 | 700000 | 96600 | 796600 | 20 | 0 | 700000 | 96600 | 70000 | 726600 | 0
C.3.2 | RCC for Foundation up- Raft including Tie beam if any | % | 40 | 35000 | 1400000 | 193200 | 1593200 | 36 | 4 | 1260000 | 173880 | 126000 | 1307880 | 140000
C.3.3 | RCC Column/Pedestal above Raft to Bolt level | % | 40 | 35000 | 1400000 | 193200 | 1593200 | 36 | 4 | 1260000 | 173880 | 126000 | 1307880 | 140000
C.4 | Ballistic separator foundation work for stream A,B,C | Sets | 3
C.4.1 | Exavation | % | 20 | 30000 | 600000 | 82800 | 682800 | 13 | 7 | 390000 | 53820 | 39000 | 404820 | 210000
C.4.2 | RCC for Foundation up- Raft including Tie beam if any | % | 40 | 30000 | 1200000 | 165600 | 1365600 | 27 | 13 | 810000 | 111780 | 81000 | 840780 | 390000
C.4.3 | RCC Column/Pedestal above Raft to Bolt level | % | 40 | 30000 | 1200000 | 165600 | 1365600 | 26 | 14 | 780000 | 107640 | 78000 | 809640 | 420000
C.5 | New column in exiting Shed | Nos | 16
C.5.1 | Exavation | % | 20 | 18000 | 360000 | 49680 | 409680 | 20 | 0 | 360000 | 49680 | 36000 | 373680 | 0
C.5.2 | RCC for Foundation - Raft | % | 40 | 18000 | 720000 | 99360 | 819360 | 40 | 0 | 720000 | 99360 | 72000 | 747360 | 0
C.5.3 | Back filling and compaction | % | 40 | 18000 | 720000 | 99360 | 819360 | 40 | 0 | 720000 | 99360 | 72000 | 747360 | 0
C.6 | RCC flooring/grade slab inside shed area with integrated equipment Shredder,trommel and ADS foundations etc.
C.6.1 | Shredder Foundation work | Nos | 3 | 1500000 | 4500000 | 621000 | 5121000 | 3 | 0 | 4500000 | 621000 | 450000 | 4671000 | 0
C.6.2 | trommel foundation work | Nos | 3 | 1500000 | 4500000 | 621000 | 5121000 | 2 | 1 | 3000000 | 414000 | 300000 | 3114000 | 1500000
C.6.3 | ADS foundation work | Nos | 3 | 1500000 | 4500000 | 621000 | 5121000 | 1 | 2 | 1500000 | 207000 | 150000 | 1557000 | 3000000
C.6.4 | Miscellaneous on grade slab footing if any | Sets | 3 | 541666.666 | 1624999.998 | 224249.9997 | 1849249.9977 | 1 | 2 | 541666.666 | 74749.9999 | 54166.6666 | 562249.9993 | 1083333.332
C.7 | RDF Silo Foundations for stream A,B,C | Sets | 3
C.7.1 | Exavation | % | 20 | 44250 | 885000 | 122130 | 1007130 | 6 | 14 | 265500 | 36639 | 26550 | 275589 | 619500
C.7.2 | RCC for Foundation up- Raft including Tie beam if any | % | 40 | 44250 | 1770000 | 244260 | 2014260 | 13 | 27 | 575250 | 79384.5 | 57525 | 597109.5 | 1194750
C.7.3 | RCC Column/Pedestal above Raft to Bolt level | % | 40 | 44250 | 1770000 | 244260 | 2014260 | 13 | 27 | 575250 | 79384.5 | 57525 | 597109.5 | 1194750
C.8 | Post processing equiment foundation ( in side the shed area) for stream A,B,C | Sets | 3
C.8.1 | Exavation | % | 20 | 17500 | 350000 | 48300 | 398300 | 6 | 14 | 105000 | 14490 | 10500 | 108990 | 245000
C.8.2 | RCC for Foundation - Raft | % | 40 | 17500 | 700000 | 96600 | 796600 | 13 | 27 | 227500 | 31395 | 22750 | 236145 | 472500
C.8.3 | Back filling and compaction | % | 40 | 17500 | 700000 | 96600 | 796600 | 13 | 27 | 227500 | 31395 | 22750 | 236145 | 472500
d | CIVIL WORKS FOR TANKS, TRENCHES AND ROADS/PAVEMENTS
D1 | ROADS/PAVEMENTS | Set | 1
D1.1 | Excavation Works |  | 10 | 202812.9 | 2028129 | 279881.802 | 2308010.802 |  | 10 | 0 | 0 | 0 | 0 | 2028129
D1.2 | Preparation of sub grade(WBM/PCC/DLC) |  | 40 | 202812.925 | 8112517 | 1119527.346 | 9232044.346 |  | 40 | 0 | 0 | 0 | 0 | 8112517
D1.3 | RCC/PQC |  | 50 | 202812.94 | 10140647 | 1399409.286 | 11540056.286 |  | 50 | 0 | 0 | 0 | 0 | 10140647
D2 | DRAIN
D2.1 | Drain along the road |  | 100 | 60000 | 6000000 | 828000 | 6828000 |  | 100 | 0 | 0 | 0 | 0 | 6000000
e | CIVIL WORKS FOR BUILDING(S) | Lot | 1 |  |  | 0 | 0
E.1 | Exavation | % | 5% | 760000 | 760000 | 104880 | 864880 | 5% | 0% | 760000 | 104880 | 76000 | 788880 | 0
E.2 | RCC Column from Raft to Plinth beam bottom | % | 15% | 2280000 | 2280000 | 314640 | 2594640 | 15% | 0% | 2280000 | 314640 | 228000 | 2366640 | 0
E.3 | RCC Plinth beam | % | 10% | 1520000 | 1520000 | 209760 | 1729760 | 10% | 0% | 1520000 | 209760 | 152000 | 1577760 | 0
E.4 | Columns up to roof slab bottom level | % | 15% | 2280000 | 2280000 | 314640 | 2594640 | 15% | 0% | 2280000 | 314640 | 228000 | 2366640 | 0
E.5 | RCC for Floor Roof slab casting level | % | 20% | 3040000 | 3040000 | 419520 | 3459520 | 20% | 0% | 3040000 | 419520 | 304000 | 3155520 | 0
E.6 | Brick Masonry work With plaster work | % | 5% | 760000 | 760000 | 104880 | 864880 | 0% | 5% | 0 | 0 | 0 | 0 | 760000
E.7 | Completion of Flooring/Grade slab | % | 15% | 2280000 | 2280000 | 314640 | 2594640 | 12% | 3% | 1824000 | 251712 | 182400 | 1893312 | 456000
E.8 | Finished of work | % | 15% | 2280000 | 2280000 | 314640 | 2594640 | 0% | 15% | 0 | 0 | 0 | 0 | 2280000
f | CIVIL WORKS FOR SILOS & CONVEYOR SYSTEM
F1 | Char/Pillet Silo Foundation | Sets | 2
F1.1 | Pile | % | 40% | 5200000 | 5200000 | 717600 | 5917600 | 20% | 20% | 2600000 | 358800 | 260000 | 2698800 | 1040000
F1.2 | Excavation | % | 10% | 1300000 | 1300000 | 179400 | 1479400 | 0% | 10% | 0 | 0 | 0 | 0 | 130000
F1.3 | Raft foundation | % | 40% | 5200000 | 5200000 | 717600 | 5917600 |  | 40% | 0 | 0 | 0 | 0 | 2080000
F1.4 | Backfilling | % | 10% | 1300000 | 1300000 | 179400 | 1479400 |  | 10% | 0 | 0 | 0 | 0 | 130000
F2 | Inert Silo and Fe-Inert Silo foundation | Sets | 6
F2.1 | Excavation | % | 50% | 600000 | 600000 | 82800 | 682800 |  | 50% | 0 | 0 | 0 | 0 | 300000
F2.2 | RCC for Foundation | % | 50% | 600000 | 600000 | 82800 | 682800 |  | 50% | 0 | 0 | 0 | 0 | 300000
F3 | Intergreted grade slab for conveyor system and Grade slab inside of shed area. | Set | 1
F3.1 | RCC flooring | % | 80 | 126810.8625 | 10144869 | 1399991.922 | 11544860.922 | 50 | 30 | 6340543.125 | 874994.9513 | 634054.3125 | 6581483.7637 | 3804325.875
F3.2 | IPS flooring | % | 20 | 131810.85 | 131810.85 | 18189.8973 | 150000.7473 |  | 20 | 0 | 0 | 0 | 0 | 2636217
g | OTHER CIVIL/FOUNDATION WORKS ( LTP, ETP, FIRE WATER PUMP HOUSE, RAIN WATER HARVESTING AND HORTICULTURE ETC.) | Lot | 1 | 23861215
G1 | VFD CONTROL ROOM PLC BUILDING | No. | 100%
G.1.1 | Excavation |  | 5% | 675000 | 675000 | 93150 | 768150 | 5% | 0% | 675000 | 93150 | 67500 | 700650 | 0
G.1.2 | RCC Column from Raft to Plinth beam bottom |  | 15% | 2025000 | 2025000 | 279450 | 2304450 | 15% | 0% | 2025000 | 279450 | 202500 | 2101950 | 0
G.1.3 | RCC Plinth beam |  | 10% | 1350000 | 1350000 | 186300 | 1536300 | 10% | 0% | 1350000 | 186300 | 135000 | 1401300 | 0
G.1.4 | Columns up to roof slab bottom level |  | 15% | 2025000 | 2025000 | 279450 | 2304450 | 15% | 0% | 2025000 | 279450 | 202500 | 2101950 | 0
G.1.5 | RCC for Floor Roof slab casting level |  | 20% | 2700000 | 2700000 | 372600 | 3072600 | 20% | 0% | 2700000 | 372600 | 270000 | 2802600 | 0
G.1.6 | Brick Masonry work With plaster work |  | 5% | 675000 | 675000 | 93150 | 768150 | 5% | 0% | 675000 | 93150 | 67500 | 700650 | 0
G.1.7 | Completion of Flooring/Grade slab |  | 15% | 2025000 | 2025000 | 279450 | 2304450 | 15% | 0% | 2025000 | 279450 | 202500 | 2101950 | 0
G.1.8 | Finished of work |  | 15% | 2025000 | 2025000 | 279450 | 2304450 |  | 15% | 0 | 0 | 0 | 0 | 303750
G2 | LEACHATE & EFFLUENT TREATMENT PLANT CIVIL WORK | Lot | 1 | 1500000 | 1500000 | 207000 | 1707000 |  | 1 | 0 | 0 | 0 | 0 | 1500000
G3 | WATER HARVESTING & GREEN AREA | Lot | 1 | 2500000 | 2500000 | 345000 | 2845000 |  | 1 | 0 | 0 | 0 | 0 | 2500000
G4 | FIRE WATER PUMP HOUSE | Nos | 1 | 1000000 | 1000000 | 138000 | 1138000 |  | 1 | 0 | 0 | 0 | 0 | 1000000
G5 | WEIGH BRIDGE AREA CIVIL WORK | Nos | 2 | 500000 | 1000000 | 138000 | 1138000 |  | 2 | 0 | 0 | 0 | 0 | 1000000
G6 | DG ARAE CIVIL WORK | Nos | 1 | 1000000 | 1000000 | 138000 | 1138000 |  | 1 | 0 | 0 | 0 | 0 | 1000000
G7 | TRANSFORMER ARAE CIVIL WORK | Nos | 2 | 750000 | 1500000 | 207000 | 1707000 |  | 2 | 0 | 0 | 0 | 0 | 1500000
G8 | MISCELLANEOUS WORKS-NOT COVERED IN ABOVE WORKS | Lot | 1 | 1861215 | 1861215 | 256847.67 | 2118062.67 |  | 1 | 0 | 0 | 0 | 0 | 1861215
C | Site Fabricated Steel Structure | [7 empty] | 0 |  |  |  |  | 0
i | Supply , Fabrication, & erection of site fabricated steel structure works | Lot | 1 | 50000000
1 | Site fabrication works for existing shed Strengthening
a | Lot 1 Supply | MT | 145 | 131896.5517 | 19125000 | 2639250 | 21764250 | 145 | 0 | 19125000 | 2639250 | 1912500 | 19851750 | 0 |  | 23323965.5172
b | Lot2 Fabrication | MT | 145 | 63620.6897 | 9225000 | 1273050 | 10498050 | 42 | 103 | 2672068.9655 | 368745.5172 | 267206.8966 | 2773607.5862 | 6552931.0345
c | Lot 3 Erection | MT | 145 | 45000 | 6525000 | 900450 | 7425450 | 21 | 124 | 945000 | 130410 | 94500 | 980910 | 5580000
d | Lot 4 Final Alignment | MT | 145 | 38793.1034 | 5625000 | 776250 | 6401250 | 15 | 130 | 581896.5517 | 80301.7241 | 58189.6552 | 604008.6207 | 5043103.4483
e | Lot 5 Operational Acceptance | MT | 145 | 31034.4828 | 4500000 | 621000 | 5121000 |  | 145 | 0 | 0 | 0 | 0 | 4500000
2 | Site fabrication works Pre-processing system | Lot | 1 | 1666667 | 1666667 | 230000.046 | 1896667.046 |  | 1 | 0 | 0 | 0 | 0 | 1666667
3 | Site fabrication works Reactor and auxiliary system | Lot | 1 | 1666667 | 1666667 | 230000.046 | 1896667.046 |  | 1 | 0 | 0 | 0 | 0 | 1666667
4 | Site fabrication works for miscellaneous | Lot | 1 | 1666667 | 1666667 | 230000.046 | 1896667.046 |  | 1 | 0 | 0 | 0 | 0 | 1666667
D | Training Charges
1 | O&M PERSONAL TRAINING | Man-Month | 2 | 200000 | 400000 | 55200 | 455200 |  | 2 | 0 | 0 | 0 | 0 | 400000
2 | ENGINEERING PERSONAL | Man-Month | 1 | 100000 | 100000 | 13800 | 113800 |  | 1 | 0 | 0 | 0 | 0 | 100000 | 296238048.6898
6 | Amount Linked to Safety Aspects | Lot | 1 | 11000000 | 11000000 | 1518000 | 12518000 |  | 1 | 0 | 0 | 0 | 0 | 11000000