## Sheet1
| ATLI Sohana | BSL Kharkhoda | BSL Manesar
Contact Person | Deepanshu Beriwal | Mithilesh Singh | Surya Sankar Das
Contact Number | 7027180003 | 9452997756 | 9040460587
Project Details | The 2.7 MW rooftop solar project located in the Sohana district of Haryana is currently in its initial phase. The structural components have already been delivered to the site, and activities such as site marking and material shifting are actively underway.The solar modules are presently in transit and are expected to arrive at the project location by 25 May 2025. The project is on track and is scheduled for commissioning by 25 August 2025. | The 365 kWp rooftop solar project, located in the Sonipat district of Haryana, is currently in its mid-phase of execution. The majority of the project materials have been delivered to the site, with the exception of the solar modules, which are expected to arrive by the end of May 2025.Ongoing activities include the installation of the walkway and structural components. The project remains on schedule and is targeted for commissioning by 10 June 202 | The 365 kWp rooftop solar project located in the Sonipat district of Haryana has been successfully commissioned. The project has been completed as per schedule, and the handover to the Operations & Maintenance (O&M) team has been completed. All systems are now operational, and the site is under the supervision of the O&M team for ongoing performance monitoring and maintenance.
Project Timelines | 2025-08-01 | 2025-06-10 | Commissioned